## Summary
Discipline | AFC | IFC | IFA | IFR | IDC | DUE | Total | PlannedWtg | EarnedWtg | CompletionPct
PROCESS | 55 | 0 | 12 | 10 | 0 | 10 |  | 0.1287 | 0.09491
EQUIPMENT | 72 | 0 | 33 | 19 | 0 | 4 |  | 0.195 | 0.14617
PIPING | 29 | 1 | 11 | 21 | 1 | 29 |  | 0.1288 | 0.06167
FIRE PROTECTION | 12 | 0 | 21 | 4 | 0 | 3 |  | 0.06 | 0.039975
CIVIL | 45 | 0 | 38 | 4 | 0 | 0 |  | 0.1218 | 0.09667
STRUCTURAL | 0 | 0 | 12 | 22 | 0 | 0 |  | 0.0476 | 0.02324
ELECTRICAL | 44 | 7 | 7 | 6 | 5 | 13 |  | 0.1148 | 0.07714
INSTRUMENTATION | 32 | 0 | 5 | 34 | 1 | 29 |  | 0.147 | 0.06636
PROJECTS | 12 | 0 | 0 | 0 | 0 | 0 |  | 0.0182 | 0.01596
HSE | 1 | 0 | 1 | 1 | 0 | 0 |  | 0.007 | 0.0028
TOTAL

## DCI
Discipline | DocNum | DocDesc | SubFormat | ApprovalCat | Weitage | InitSchedule | LatestRev | LatestStatus | PctWeitage | Remarks
HSE | VTV-3281-HSE-001 | EMERGENCY RESPONSE PLAN | PDF | R | 0.0014 | 2020-07-10 |  | AFC | 0.00133
HSE | VTV-3281-HSE-004 | ENVIRONMENT MANAGEMENT PLAN | PDF | R | 0.0014 | 2020-08-10 |  | IFA | 0.00091
HSE | VTV-3281-HSE-005 | HIRA FOR WORK AT HEIGHT,ERECTION,AREA DEVELOPMENT,EXCAVATION,PILING,LOADING,UNLOADING AND SHIFTING OF MATERIALS,WELDING,CUTTING,GRINDING,RADIOGRAPHY,BLASTING AND PAINTING | PDF | R | 0.0014 | 2020-08-10 |  | IFR | 0.00056
EQUIPMENT | VTV-3281-LIT- 9511-TK-CAL-001 | TANK DESIGN CALCULATION INCLUDING TANK CAPACITY CALCULATION | PDF | A | 0.0015 | 2020-06-01 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-CAL-002 | HEAT LEAK CALCULATION | PDF | A | 0.0015 | 2020-07-08 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-CAL-003 | DOME ROOF STRUCTURE DESIGN CALCULATION | PDF | A | 0.0015 | 2020-07-27 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-CAL-004 | SUSPENDED DECK DESIGN CALCULATION | PDF | A | 0.0015 | 2020-08-12 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-CAL-005 | NOZZLE REINFORCEMENT DESIGN CALCULATION | PDF | A | 0.0015 | 2020-08-26 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-CAL-006 | DESIGN OF CONSTRUCTION MONORAIL | PDF | A | 0.0015 | 2020-07-27 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DOC-001 | TECHNICAL DELIVERY CONDITION FOR STAINLESS STEEL MATERIAL | PDF | I | 0.0015 | 2020-07-31 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DOC-002 | MR FOR INSULATION MATERIAL | PDF | I | 0.0015 | 2020-08-07 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DOC-003 | QAP FOR INSULATION MATERIAL | PDF | I | 0.0015 | 2020-08-07 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-001 | DETAIL OF GENERAL ARRANGEMENT DRAWING | PDF | A | 0.0015 | 2020-06-01 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-002 | DETAIL OF TANK INTERFACE DIMENSIONS | PDF | A | 0.0015 | 2020-08-31 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-003 | ROOF NOZZLE ORIENTATION | PDF | A | 0.0015 | 2020-08-07 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-004 | TANK FOUNDATION LOADING DATA | PDF | A | 0.0015 | 2020-06-01 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-005 | ANCHOR STRAP (SETTING PLAN) | PDF | A | 0.0015 | 2020-09-14 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-006 | ANCHOR STRAP DETAIL | PDF | A | 0.0015 | 2020-09-14 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-007 | INNER TANK BOTTOM LAYOUT WITH ANNULAR PLATES | PDF | A | 0.0015 | 2020-09-18 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-008 | INNER TANK SHELL STIFFINERS | PDF | A | 0.0015 | 2020-09-18 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-009 | INNER TANK SHELL LAYOUT | PDF | A | 0.0015 | 2020-09-18 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-010 | OUTER TANK BOTTOM LAYOUT WITH ANNULAR PLATES | PDF | A | 0.0015 | 2020-07-10 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-011 | OUTER TANK SHELL LAYOUT | PDF | A | 0.0015 | 2020-08-07 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-012 | OUTER TANK SHELL STIFFENERS | PDF | A | 0.0015 | 2020-08-07 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-013 | DETAIL OF SUSPENDED DECK HANGERS AND STIFFENERS | PDF | A | 0.0015 | 2020-09-04 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-014 | DETAIL OF SUSPENDED DECK LAYOUT | PDF | A | 0.0015 | 2020-09-04 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-015 | DETAIL OF SUSPENDED DECK SLEEVE | PDF | A | 0.0015 | 2020-09-04 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-016 | DETAIL OF TANK ROOF GENERAL ARRANGEMENT | PDF | A | 0.0015 | 2020-07-27 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-017 | DETAIL OF MAIN RAFTER | PDF | A | 0.0015 | 2020-07-27 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-018 | DETAIL OF LATERAL BEAM | PDF | A | 0.0015 | 2020-07-27 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-019 | DETAIL OF CENTER DRUM | PDF | A | 0.0015 | 2020-07-27 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-020 | DETAIL OF ROOF BRACING | PDF | A | 0.0015 | 2020-07-27 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-021 | DETAIL OF CONSTRUCTION MONORAIL | PDF | A | 0.0015 | 2020-07-27 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-022 | DETAIL OF DOME ROOF PLATES WITH COMPRESSION BAR | PDF | A | 0.0015 | 2020-07-27 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-023 | DETAIL OF ROOF MANHOLE N1 | PDF | A | 0.0015 | 2020-09-09 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-024 | DETAIL OF ROOF MANHOLE N2 | PDF | A | 0.0015 | 2020-09-09 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-025 | DETAIL OF PUMP COLUMNS N4A/N4B/N4C | PDF | A | 0.0015 | 2020-10-14 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-026 | DETAIL OF PUMP DISCHARGE N5A-C,COLUMN PURGE TOP N6A-C | PDF | A | 0.0015 | 2020-10-14 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-027 | DETAIL OF LEFT BLANK NOZZLE N3 | PDF | A | 0.0015 | 2020-10-14 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-028 | DETAIL OF COLUMN PURGE BOTTOM NOZZLE N7A-C | PDF | A | 0.0015 | 2020-10-14 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-029 | DETAIL OF FILLING NOZZLE N8A-B | PDF | A | 0.0015 | 2020-09-14 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-030 | DETAIL OF COMPRESSOR SUCTION NOZZLE N9 | PDF | A | 0.0015 | 2020-09-14 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-031 | DETAIL OF TOP SPRAY N10 | PDF | A | 0.0015 | 2020-09-16 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-032 | DETAIL OF BOTTOM DISTRIBUTOR NOZZLE N11 | PDF | A | 0.0015 | 2020-09-21 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-033 | DETAIL OF PUMP RETURN NOZZLE N12 | PDF | A | 0.0015 | 2020-09-21 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-034 | DETAIL OF OUTER TANK PURGE NOZZLE N13 | PDF | A | 0.0015 | 2020-09-25 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-035 | DETAIL OF ROOF VENT NOZZLE (INNER TANK) N14 | PDF | A | 0.0015 | 2020-09-25 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-036 | DETAIL OF LEVEL TRANSMITTER NOZZLE (N15A-B) | PDF | A | 0.0015 | 2020-09-30 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-037 | DETAIL OF TEMP TRANSMITTER NOZZLE (N15C-D) | PDF | A | 0.0015 | 2020-09-30 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-038 | DETAIL OF HIGH LEVEL SWITCH TRANSMITTER NOZZLE (N15E) | PDF | A | 0.0015 | 2020-09-30 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-039 | DETAIL OF VENT NOZZLE (N16) | PDF | A | 0.0015 | 2020-10-03 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-040 | DETAIL OF SAFETY RELIEF NOZZLE(N17A-E) | PDF | A | 0.0015 | 2020-10-03 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-041 | DETAIL OF PILOT SAFETY RELIEF NOZZLE(N18) | PDF | A | 0.0015 | 2020-10-03 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-042 | DETAIL OF VACUUM BREATHER NOZZLE(N19A/B) | PDF | A | 0.0015 | 2020-10-07 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-043 | DETAIL OF PRESSURE INDICATOR NOZZLE(N20A/B) | PDF | A | 0.0015 | 2020-10-07 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-044 | DETAIL OF TEMP ELEMENT(TANK WALL) N23A-C | PDF | A | 0.0015 | 2020-10-10 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-045 | DETAIL OF SPRAY NOZZLE COLD NOZZLE N24 | PDF | A | 0.0015 | 2020-10-21 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-046 | DETAIL OF SPRAY NOZZLE WARM NOZZLE N25 | PDF | A | 0.0015 | 2020-10-21 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-047 | DETAIL OF TRV DISCHARGE NOZZLE N26 | PDF | A | 0.0015 | 2020-10-21 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-048 | DETAIL OF VAPOUR RETURN NOZZLE N27 | PDF | A | 0.0015 | 2020-10-28 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-049 | DETAIL OF SPILL DETECTOR NOZZLE N29 | PDF | A | 0.0015 | 2020-10-28 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-050 | DETAIL OF ANNULAR SPACE VENT N30 | PDF | A | 0.0015 | 2020-10-28 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-051 | DETAIL OF TEMP MONITORING IN ANNULAR SPACE FOR LEAK DET.N31 | PDF | A | 0.0015 | 2020-10-28 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-052 | DETAIL OF INNER TANK PLATFORM AND LADDERS | PDF | A | 0.0015 | 2020-11-19 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-053 | DETAIL OF LADDERS IN ANNULAR SPACE | PDF | A | 0.0015 | 2020-11-19 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-054 | INSULATION DETAILS FOR BOTTOM | PDF | A | 0.0015 | 2020-08-05 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-055 | INSULATION DETAILS FOR SHELL | PDF | A | 0.0015 | 2020-10-13 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-056 | DETAILS FOR SUSPENDED DECK INSULATION | PDF | A | 0.0015 | 2020-10-20 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-057 | DETAIL OF ROOF & SHELL NOZZLES INSULATION | PDF | A | 0.0015 | 2020-10-20 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-058 | DETAILS OF EARTHING CONNECTION | PDF | A | 0.0015 | 2020-12-07 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-059 | DETAILS OF NAME PLATE & BRACKET | PDF | A | 0.0015 | 2020-12-07 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-060 | DETAILS OF SKIN TEMPERATURE ELEMENTS | PDF | A | 0.0015 | 2020-12-01 |  | AFC | 0.001425
EQUIPMENT | VTV-3281-LIT- 9511-TK-DRG-061 | DETAIL DRAWINGS OF VENT | PDF | R | 0.0015 | 2020-12-01 |  | AFC | 0.001425
CIVIL | VTV-3281-LIT-9511-CE-CAL-001 | REPORT FOR TOPOGRAPHICAL SURVEY | PDF | A | 0.0014 | 2020-07-22 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-CAL-002 | DESIGN CALCULATION REPORT FOR PILE & PILE CAP FOR TANK FOUNDATION | PDF | A | 0.0014 | 2020-07-24 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-003 | DESIGN CALCULATION REPORT FOR TANK FOUNDATION (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-08-19 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-004 | FOUNDATION CALCULATION REPORT FOR NEW FLASH GAS COMPRESSORS (K-2303 A/B) | PDF | A | 0.0014 | 2021-01-16 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-005 | FOUNDATION CALCULATION REPORT FOR NEW COMPRESSOR SHED | PDF | A | 0.0014 | 2020-10-22 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-006 | FOUNDATION DESIGN CALCULATION REPORT FOR COOLING TOWER STRUCTURE (CT-3002) | PDF | A | 0.0014 | 2021-01-22 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-007 | DESIGN CALCULATION REPORT FOR RCC COOLING TOWER BASIN (CT-3002) | PDF | A | 0.0014 | 2021-01-22 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-008 | FOUNDATION CALCULATION REPORT FOR NEW COOLING WATER CIRCULATION PUMPS (P-3003A/B/C) | PDF | A | 0.0014 | 2021-01-16 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-009 | FOUNDATION CALCULATION REPORT FOR NEW CONDENSATE TRANSFER PUMPS (P-2309R A/B) | PDF | A | 0.0014 | 2021-02-10 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-010 | FOUNDATION CALCULATION REPORT FOR FLASH GAS COMPRESSOR SUCTION SEPERATORS (B-2304A/B) | PDF | A | 0.0014 | 2021-02-10 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-011 | FOUNDATION CALCULATION REPORT FOR NEW VENT DRUM (B-2303N) | PDF | A | 0.0014 | 2021-01-07 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-012 | EXTENSION OF SUBSTATION FOUNDATION DESIGN CALCULATION REPORT | PDF | A | 0.0014 | 2020-10-23 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-013 | EXTENSION OF CCR FOUNDATION DESIGN CALCULATION REPORT | PDF | A | 0.0014 | 2020-10-23 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-014 | DESIGN CALCULATION REPORT FOR SWITCHYARD FOUNDATIONS | PDF | A | 0.0014 | 2020-11-26 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-015 | DESIGN CALCULATION REPORT FOR TRANSFORMER FOUNDATION REPORT | PDF | A | 0.0014 | 2020-10-15 |  | IFR | 0.00056
CIVIL | VTV-3281-LIT-9511-CE-CAL-016 | DESIGN CALCULATION REPORT FOR DG SET FOUNDATION | PDF | A | 0.0014 | 2020-12-18 |  | IFR | 0.00056
CIVIL | VTV-3281-LIT-9511-CE-CAL-017 | EXTENSION OF DG SHED FOUNDATION DESIGN CALCULATION REPORT | PDF | A | 0.0014 | 2020-10-21 |  | IFR | 0.00056
CIVIL | VTV-3281-LIT-9511-CE-CAL-018 | FOUNDATION DESIGN CALCULATION REPORT FOR DIESEL STORAGE DAY TANK (HSD-T-3002) | PDF | A | 0.0014 | 2020-10-17 |  | IFR | 0.00056
CIVIL | VTV-3281-LIT-9511-CE-CAL-019 | PIPE RACK STRUCTURE FOUNDATION DESIGN CALCULATION REPORT (NEW TANK AREA) | PDF | A | 0.0014 | 2020-10-16 | REV.0 | AFC | 0.00133 | SUBMITTED REV.0
CIVIL | VTV-3281-LIT-9511-CE-CAL-020 | PIPE RACK STRUCTURE FOUNDATION DESIGN CALCULATION REPORT (NEW COMPRESSOR AREA) | PDF | A | 0.0014 | 2020-10-24 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-021 | PIPE RACK STRUCTURE FOUNDATION DESIGN CALCULATION REPORT (NEW LP BOILER AREA) | PDF | A | 0.0014 | 2020-11-02 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-022 | DESIGN CALCULATION REPORT FOR STAIR TOWER (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-10-24 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-023 | DESIGN CALCULATION REPORT FOR PIPE BRIDGE WITH STAIR (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-10-24 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-024 | FOUNDATION DESIGN CALCULATION REPORT BLOW DOWN PIT PUMPS (P-3005A/B) | PDF | A | 0.0014 | 2020-12-23 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-025 | FOUNDATION DESIGN CALCULATION REPORT FOR BLOW DOWN PIT (S-3004) | PDF | A | 0.0014 | 2020-12-23 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-026 | DESIGN & CALCULATION REPORT FOR WATER SUMP | PDF | A | 0.0014 | 2021-01-23 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-027 | EFFULENT TREATMENT PLANT FOUNDATION DESIGN CALCULATION REPORT | PDF | A | 0.0014 | 2020-11-19 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-028 | CALCULATION REPORT FOR DELUGE VALVE FOUNDATION | PDF | A | 0.0014 | 2021-02-12 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-029 | CALCULATION REPORT FOR CABLE TRAY RACK FOUNDATION | PDF | A | 0.0014 | 2020-12-18 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-030 | CALCULATION REPORT FOR HIGH MAST TOWER FOUNDATION | PDF | A | 0.0014 | 2020-12-28 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-031 | DESIGN CALCULATION REPORT FOR FIRE FIGHTING SLEEPERS FOUNDATION | PDF | A | 0.0014 | 2021-01-22 | REV.03 | AFC | 0.00133 | SUBMITTED REV.03
CIVIL | VTV-3281-LIT-9511-CE-CAL-032 | STANDARD TYPICAL ROAD DESIGN CALCULATION | PDF | A | 0.0014 | 2020-10-21 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-033 | PIPE SUPPORT FOUNDATION CALCULATION REPORT | PDF | A | 0.0014 | 2021-01-19 | REV.0 | AFC | 0.00133 | SUBMITTED
CIVIL | VTV-3281-LIT-9511-CE-CAL-034 | SPECIAL PIPE SUPPORTS CALCULATION REPORT | PDF | A | 0.0014 | 2021-01-19 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-035 | CALCULATION REPORT PIPE SLEEPERS FOUNDATION | PDF | A | 0.0014 | 2021-01-19 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-CAL-036 | CALCULATION REPORT STORM WATER DRAIN | PDF | A | 0.0014 | 2021-12-23 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-DRG-001 | BORE HOLE LOCATION LAYOUT | PDF | A | 0.0014 | 2020-05-27 | REV.0 | AFC | 0.00133 | SUBMITTED
CIVIL | VTV-3281-LIT-9511-CE-DRG-002 | LAYOUT & DETAILS OF TOPOGRAPHICAL SURVEY | PDF | A | 0.0014 | 2020-07-22 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-003 | LAYOUT & DETAILS OF PILE & PILE CAP FOR TANK FOUNDATION | PDF | A | 0.0014 | 2021-07-24 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-004 | LAYOUT & DETAILS OF TANK FOUNDATION (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-08-19 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-005 | FOUNDATION DRAWING FOR STAIR TOWER (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-10-24 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-006 | FOUNDATION DRAWING FOR PIPE BRIDGE WITH STAIR (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-10-24 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-007 | COMPRESSOR FOUNDATION DETAIL DRAWING | PDF | A | 0.0014 | 2020-12-12 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-008 | COMPRESSOR SHED FOUNDATION DETAIL DRAWING | PDF | A | 0.0014 | 2020-10-22 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-009 | FOUNDATION DETAIL DRAWING FOR NEW COOLING WATER CIRCULATION PUMPS (P-3003A/B/C) | PDF | A | 0.0014 | 2021-01-16 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-010 | FOUNDATION DETAIL DRAWING FOR NEW CONDENSATE TRANSFER PUMPS (P-2309R A/B) | PDF | A | 0.0014 | 2021-02-10 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-011 | FOUNDATION DETAIL DRAWING FOR RCC COOLING TOWER BASIN (CT-3002) | PDF | A | 0.0014 | 2021-01-22 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-012 | FOUNDATION DETAIL DRAWING FOR FLASH GAS COMPRESSOR SUCTION SEPERATORS (B-2304A/B) | PDF | A | 0.0014 | 2021-02-10 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-013 | FOUNDATION DETAIL DRAWING FOR NEW VENT DRUM (B-2303N) | PDF | A | 0.0014 | 2021-01-07 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-014 | FOUNDATION DETAIL DRAWING FOR TRANSFORMER | PDF | A | 0.0014 | 2020-10-15 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-015 | ARCH.DRAWING FOR SUBSTATION EXTENSION | PDF | A | 0.0014 | 2020-11-13 | REV.02 | IFA | 0.00091 | SUBMITTED REV.02
CIVIL | VTV-3281-LIT-9511-CE-DRG-016 | EXTENSION OF SUBSTATION FOUNDATION DRAWINGS | PDF | A | 0.0014 | 2020-10-23 | REV.0 | IFA | 0.00091 | SUBMITTED REV.0
CIVIL | VTV-3281-LIT-9511-CE-DRG-017 | ARCH.DRAWING FOR EXTENSION OF CCR BUILDING | PDF | A | 0.0014 | 2020-11-13 | REV.0 | IFA | 0.00091 | SUBMITTED REV.0
CIVIL | VTV-3281-LIT-9511-CE-DRG-018 | EXTENSION OF CCR FOUNDATION DRAWINGS | PDF | A | 0.0014 | 2020-10-23 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-019 | FOUNDATION DETAIL DRAWING FOR DG SET | PDF | A | 0.0014 | 2020-12-18 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-020 | ARCH.DRAWING FOR DG SHED | PDF | A | 0.0014 | 2020-11-10 | REV.0 | IFA | 0.00091 | SUBMITTED REV.0
CIVIL | VTV-3281-LIT-9511-CE-DRG-021 | EXTENSION OF DG SHED FOUNDATION DETAIL DRAWING | PDF | A | 0.0014 | 2020-10-21 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-022 | FOUNDATION DETAIL DRAWING FOR DIESEL STORAGE DAY TANK (HSD-T-3002) | PDF | A | 0.0014 | 2020-10-17 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-023 | FOUNDATION DETAIL DRAWING FOR COOLING TOWER STRUCTURE | PDF | A | 0.0014 | 2020-10-22 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-024 | EFFULENT TREATMENT PLANT FOUNDATION DRAWING | PDF | A | 0.0014 | 2020-11-19 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-025 | PIPE RACK STRUCTURE FOUNDATION DRAWING (NEW TANK AREA) | PDF | A | 0.0014 | 2020-10-19 | REV.0 | IFA | 0.00091 | SUBMITTED REV.0
CIVIL | VTV-3281-LIT-9511-CE-DRG-026 | PIPE RACK STRUCTURE FOUNDATION DRAWING (NEW COMPRESSOR AREA) | PDF | A | 0.0014 | 2020-10-28 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-027 | PIPE RACK STRUCTURE FOUNDATION DRAWING (NEW LP BOILER AREA) | PDF | A | 0.0014 | 2020-11-06 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-028 | DETAIL DRAWING FOR BLOW DOWN PIT (S-3004) | PDF | A | 0.0014 | 2020-12-23 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-029 | BLOW DOWN PIT PUMPS FOUNDATION DETAIL DRAWING (P-3005A/B) | PDF | A | 0.0014 | 2020-12-23 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-030 | FOUNDATION DETAIL DRAWING FOR CABLE TRAY RACK | PDF | A | 0.0014 | 2020-12-18 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-031 | FOUNDATION DETAIL DRAWING FOR HIGH MAST TOWER | PDF | A | 0.0014 | 2020-12-28 | Rev.0 | AFC | 0.00133 | COMMENTS RECD. ON REV.0
CIVIL | VTV-3281-LIT-9511-CE-DRG-032 | DELUGE VALVE FOUNDATION DETAIL DRAWING | PDF | A | 0.0014 | 2021-02-12 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-DRG-033 | FOUNDATION DETAIL DRAWING FOR FIRE FIGHTING SLEEPERS | PDF | A | 0.0014 | 2021-01-22 | Rev.03 | AFC | 0.00133 | submitted REV.03
CIVIL | VTV-3281-LIT-9511-CE-DRG-034 | TYPICAL KERB WALL DETAIL DRAWING | PDF | A | 0.0014 | 2020-09-18 | Rev.00 | AFC | 0.00133 | submitted REV.00
CIVIL | VTV-3281-LIT-9511-CE-DRG-035 | PIPE SUPPORT FOUNDATION DETAIL DRAWING | PDF | A | 0.0014 | 2021-01-19 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-DRG-036 | FOUNDATION DETAIL DRAWING FOR PIPE SLEEPERS | PDF | A | 0.0014 | 2021-01-19 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-DRG-037 | STANDARD TYPICAL ROAD DRAWING | PDF | A | 0.0014 | 2020-10-21 | Rev.00 | AFC | 0.00133 | Submitted REV.00
CIVIL | VTV-3281-LIT-9511-CE-DRG-038 | DETAIL DRAWING FOR SCRAP YARD DEVELOPMENT | PDF | A | 0.0014 | 2020-09-18 | Rev.00 | AFC | 0.00133 | Submitted REV.00
CIVIL | VTV-3281-LIT-9511-CE-DRG-039 | TYP.CABLE TRENCH DETAIL DRAWING | PDF | A | 0.0014 | 2020-09-18 | Rev.01 | AFC | 0.00133 | Submitted REV.01
CIVIL | VTV-3281-LIT-9511-CE-DRG-040 | TYP.DETAIL DRAWING OF PIPE CULVERT DETAILS | PDF | A | 0.0014 | 2020-09-18 | Rev.0 | AFC | 0.00133 | COMMENTS RECD. ON REV.0
CIVIL | VTV-3281-LIT-9511-CE-DRG-041 | STORM WATER DRAIN DRAWING | PDF | A | 0.0014 | 2021-12-23 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-DRG-042 | TYPICAL DETAILS FOR GRADING | PDF | A | 0.0014 | 2020-09-18 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-DRG-043 | CIVIL DRAWING FOR DV HOUSING | PDF | A | 0.0014 | 2020-10-23 |  | AFC | 0.00133
CIVIL | VTV-3281-LIT-9511-CE-DRG-044 | GENERAL ARRANGENMENT DRAWING OF SUB STATION | PDF | A | 0.0014 | 2020-10-24 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-045 | GENERAL ARRANGENMENT DRAWING OF D.G. SET ROOM | PDF | A | 0.0014 | 2020-12-18 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-046 | GENERAL ARRANGENMENT DRAWING OF CONTROL ROOM | PDF | A | 0.0014 | 2020-10-23 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-047 | GENERAL ARRANGENMENT DRAWING OF SWITCH YARD ROOM | PDF | A | 0.0014 | 2020-10-16 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-048 | GENERAL ARRANGENMENT DRAWING OF PIPE RACK LAYOUT, | PDF | A | 0.0014 | 2020-10-16 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-049 | GENERAL ARRANGENMENT DRAWING OF STORM WATER DRAIN | PDF | A | 0.0014 | 2021-12-23 |  | IFA | 0.00091
CIVIL | VTV-3281-LIT-9511-CE-DRG-052 | ARCHITECTURAL DRAWING FOR METERING ROOM AT SWITCH YARD AREA |  |  | 0.0014 |  | REV.0 | IFA | 0.00091 | SUBMITTED REV.0
CIVIL | VTV-3281-LIT-9511-CE-DRG-053 | FOUNDATION DETAIL DRAWING FOR METERING ROOM AT SWITCH YARD AREA |  |  | 0.0014 |  | REV.0 | IFA | 0.00091 | SUBMITTED REV.0
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-001 | TRANSFORMER SIZING CALCULATIONS | PDF | A | 0.0014 | 15-07-2020 | REV.02 | IFC | 0.00112 | SUBMITTED REV.02
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-002 | NER SIZING CALCULATIONS | PDF | A | 0.0014 | 2020-08-02 | REV.0 | AFC | 0.00133 | COMMENTS RECD. ON REV.0
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-003 | DG SIZING CALCULATIONS | PDF | A | 0.0014 | 15-07-2020 | REV.01 | IFC | 0.00112 | SUBMITTED REV.01
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-004 | DC LOAD CALCULATION | PDF | A | 0.0014 | 2020-09-07 | REV.00 | IFC | 0.00112 | COMMENTS RECD. ON REV.0
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-005 | HV CAPACITOR BANK SIZING CALCULATION | PDF | A | 0.0014 | 2020-08-10 | REV.03 | AFC | 0.00133 | COMMENTS RECD. ON REV.03
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-006 | EARTHING CALCULATIONS FOR 66KV SWITCH YARD | PDF | A | 0.0014 | 2020-08-12 | REV.02 | AFC | 0.00133 | SUBMITTED REV.02
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-007 | EARTHING CALCULATIONS FOR SWITCHGEAR BUILDING (EXTENSION) | PDF | A | 0.0014 | 2020-10-25 | REV.0 | AFC | 0.00133 | COMMENTS RECD. ON REV.00
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-008 | EARTHING CALCULATIONS FOR CONTROL ROOM BUILDING (EXTENSION) | PDF | A | 0.0014 | 2020-10-24 | REV.0 | AFC | 0.00133 | SUBMITTED
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-009 | EARTHING CALCULATIONS - NEW FACILITIES | PDF | A | 0.0014 | 2020-08-15 | REV.01 | AFC | 0.00133 | SUBMITTED REV.01
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-010 | CABLE SIZING CALCULATIONS FOR LV & MV POWER CABLES | PDF | A | 0.0014 | 2020-11-25 | REV.0 | IFA | 0.00091 | RECD. Comments on REV.00
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-011 | CABLE TRAY/ TRENCH SIZING CALCULATIONS | PDF | A | 0.0014 | 2020-11-25 |  | IFR | 0.00056
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-012 | ILLUMINATION CALCULATION REPORT FOR SWITCHGEAR BUILDING & DG ROOM | PDF | A | 0.0014 | 2020-10-25 | REV.0 | IFA | 0.00091 | RECD. Comments on REV.00
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-013 | ILLUMINATION CALCULATION REPORT FOR CONTROL ROOM BUILDING | PDF | A | 0.0014 | 2020-11-03 | REV.0 | AFC | 0.00133 | SUBMITTED REV.0
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-014 | ILLUMINATION CALCULATION REPORT FOR OUTDOOR | PDF | A | 0.0014 | 2020-12-10 | REV.0 | IFC | 0.00112 | SUBMITTED REV.0
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-015 | LIGHTNING PROTECTION CALCULATION | PDF | A | 0.0014 | 2020-08-20 | REV.0 | IFA | 0.00091 | RECD. Comments on REV.0
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-016 | HVAC SIZING CALCULATIONS FOR CONTROL ROOM BUILDINGS - EXTENSION PART | PDF | A | 0.0014 | 2021-01-27 |  | IFC | 0.00112
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-017 | RELAY COORDINATION & SETTINGS REPORT | PDF | R | 0.0014 | 2021-02-15 |  | IDC | 0.00021
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-018 | LOAD FLOW & SHORT-CIRCUIT CALCULATIONS WITH MOTOR STARTING | PDF | A | 0.0014 | 2020-08-23 | REV.0 | AFC | 0.00133 | RECD. Comments on REV.0
ELECTRICAL | VTV-3281-LIT-9511-EL-CAL-019 | HVAC DESIGN CALCULATIONS - CONTROL ROOM EXTENSION | PDF | A | 0.0014 | 2020-08-25 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-001 | ELECTRICAL - LOAD SCHEDULE | PDF | A | 0.0014 | 2020-08-03 | REV.03 | AFC | 0.00133 | SUBMITTED REV.03
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-001A | ELECTRICAL – LOAD SCHEDULE (NEW) |  |  | 0.0014 |  | REV.03 | AFC | 0.00133 | COMMENTS RECD ON REV.03
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-002 | ELECTRICAL - CABLE SCHEDULE | PDF | R | 0.0014 | 2020-12-05 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-003 | PR FOR 66/6.6KV 8MVA POWER TRANSFORMER | PDF | A | 0.0014 | 2020-09-13 | REV.0 | AFC | 0.00133 | SUBMITTED
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-004 | PR FOR 415V, 250KVA LIGHTING TRANSFORMER | PDF | A | 0.0014 | 2020-09-18 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-005 | PR FOR 66KV OUTDOOR SWITCHGEAR | PDF | A | 0.0014 | 2020-10-11 | REV.05 | AFC | 0.00133 | COMMENTS RECD ON REV.05
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-006 | PR FOR 6.6KV SWITCHGEAR | PDF | A | 0.0014 | 2020-10-11 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-007 | PR FOR 6.6KV SOFT STARTER | PDF | A | 0.0014 | 2020-10-08 | REV.01 | AFC | 0.00133 | SUBMITTED REV.01
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-008 | PR/MR FOR LV PMCC | PDF | A | 0.0014 | 2020-10-13 | REV.01 | AFC | 0.00133 | SUBMITTED REV.01
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-009 | PR FOR 6.6KV 3750KVA DG SET | PDF | A | 0.0014 | 2020-08-20 | REV.0 | AFC | 0.00133 | SUBMITTED
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-010 | PR FOR APFC & CAPACITOR BANK | PDF | A | 0.0014 | 2020-09-05 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-011 | PR FOR LUMINAIRES AND ACCESSORIES | PDF | A | 0.0014 | 2020-09-25 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-012 | PR FOR LIGHTING AND SMALL POWER PANELS | PDF | A | 0.0014 | 2020-09-30 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-013 | PR FOR HV & LV POWER AND CONTROL CABLES | PDF | A | 0.0014 | 2021-01-19 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-014 | PR FOR HVAC SYSTEM (CONTROL ROOM EXTENSION) | PDF | A | 0.0014 | 2021-01-11 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-015 | PR FOR ELECTRICAL CABLE TRAY & ACCESSORIES | PDF | A | 0.0014 | 2021-01-29 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-016 | MR/ PR FOR NEUTRAL EARTHING RESISTOR | PDF | A | 0.0014 | 2020-08-20 | REV.0 | AFC | 0.00133 | SUBMITTED REV.0
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-017 | PR FOR HIGH MAST | PDF | A | 0.0014 | 2020-10-10 | REV.0 | AFC | 0.00133 | SUBMITTED REV.0
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-018 | PR FOR FLAMEPROOF ITEMS (LCS, SW. SOCKETS, JBS ETC.) | PDF | A | 0.0014 | 2020-11-07 |  | IFA | 0.00091
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-019 | TYPICAL INSTALLATION DETAILS FOR ELECTRICAL ITEMS | PDF | I | 0.0014 | 2020-10-20 |  | IFA | 0.00091
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-020 | SPARE LIST FOR ELECTRICAL ITEMS | PDF | A | 0.0014 | 2021-05-20 |  | IDC | 0.00021
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-021 | PA SYSTEM LOCATION & CABLE ROUTING LAYOUT | PDF | A | 0.0014 | 2020-10-12 |  | IFR | 0.00056
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-022 | PR FOR PA SYSTEM | PDF | A | 0.0014 | 2021-03-29 |  | IFR | 0.00056
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-023 | PRE COMMISSIONING CHECK LIST FOR ALL ELECTRICAL EQUIPMENT. | PDF | I | 0.0014 | 2021-06-29 |  | IDC | 0.00021
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-024 | FORMAT FOR TESTING AND COMMISSIONING REPORT FOR ALL ELECTRICAL EQUIPMENT | PDF | I | 0.0014 | 2021-06-29 |  | IDC | 0.00021
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-025 | MR FOR 66KV OUTDOOR SWITCHYARD | PDF | R | 0.0014 | 2020-10-15 | REV.05 | AFC | 0.00133 | commts recd on Rev.05
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-026 | MR FOR 6.6KV 3750KVA DG SET | PDF | R | 0.0014 | 2020-09-29 | REV.02 | AFC | 0.00133 | commts recd on Rev.02
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-028 | MR FOR LV PMCC |  |  | 0.0014 |  | REV.0 | AFC | 0.00133 | commts recd on Rev.00
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-029 | MR FOR 110V AC UPS SYSTEM |  |  | 0.0014 |  | REV.0 | AFC | 0.00133 | Submitted REV.00
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-030 | MR FOR 110VDC BATTERY CHARGER |  |  | 0.0014 |  | REV.0 | AFC | 0.00133 | Submitted REV.00
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-033 | MR FOR LV POWER AND CONTROL CABLES |  |  | 0.0014 |  |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-034 | MR FOR HV CABLES |  |  | 0.0014 |  |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DOC-035 | PR FOR HV CABLES |  |  | 0.0014 |  |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-001 | SCHEMATIC DIAGRAMS- 6.6KV SWGR | PDF | A | 0.0014 | 2020-10-20 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-002 | SINGLE LINE DIAGRAM - 6.6KV SWITCHGEAR | PDF | A | 0.0014 | 2020-07-30 | REV.01 | AFC | 0.00133 | RECD. Comments on REV.01
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-003 | SINGLE LINE DIAGRAM - LV MCC | PDF | A | 0.0014 | 2020-08-05 | REV.01 | AFC | 0.00133 | SUBMITTED REV.01
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-004 | SINGLE LINE DIAGRAM - CONTROL ROOM BUILDING LIGHTING DB | PDF | A | 0.0014 | 2020-08-10 |  | IFC | 0.00112
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-005 | SINGLE LINE DIAGRAM - SWITCHGEAR ROOM LIGHTING DB | PDF | A | 0.0014 | 2020-08-12 |  | IFC | 0.00112
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-006 | OVERALL SLD | PDF | A | 0.0014 | 2020-07-27 |  | IFR | 0.00056
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-007 | 66KV SWITCHYARD LAYOUT | PDF | R | 0.0014 | 2020-07-20 | REV.03 | AFC | 0.00133 | SUBMITTED REV.03
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-008 | EQUIPMENT LAYOUT - SUBSTATION EXTENSION | PDF | A | 0.0014 | 2020-10-25 | REV.02 | AFC | 0.00133 | RECD. Comments on REV.02
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-009 | EARTHING LAYOUT - SUBSTATION EXTENSION | PDF | R | 0.0014 | 2020-09-25 | REV.02 | AFC | 0.00133 | SUBMITTED REV.02
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-010 | EARTHING LAYOUT - OUTDOOR | PDF | R | 0.0014 | 2020-12-15 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-011 | OVERALL CABLE ROUTING LAYOUT | PDF | R | 0.0014 | 2020-12-18 |  | IFR | 0.00056
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-012 | LIGHTING LAYOUT - SWITCHGEAR ROOM & CONTROL ROOM (EXTENSION) | PDF | R | 0.0014 | 2020-09-15 | REV.00 | IFA | 0.00091 | SUBMITTED REV.00
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-013 | LIGHTING LAYOUT - OUTDOOR | PDF | R | 0.0014 | 2020-09-04 |  | IFA | 0.00091
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-014 | LIGHTING & SMALL POWER PANEL SCHEDULE | PDF | R | 0.0014 | 2020-09-04 |  | IFR | 0.00056
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-015 | LIGHTNING PROTECTION SYSTEM LAYOUT - - 66KV SWITCHGEAR / SWITCHGEAR ROOM | PDF | R | 0.0014 | 2020-09-14 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-016 | LIGHTNING PROTECTION LAYOUT- OUTDOOR (FOR TANK/ COMPRESSOR HOUSE, ETC) | PDF | R | 0.0014 | 2021-01-20 |  | AFC | 0.00133
ELECTRICAL | VTV-3281-LIT-9511-EL-DRG-017 | INTERCONNECTION & TERMINAL DIAGRAMS FOR ELECTRICAL EQUIPMENT | PDF | R | 0.0014 | 2021-01-20 |  | IDC | 0.00021
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-001 | ITP FOR 66/6.6KV 8MVA POWER TRANSFORMER | PDF | A | 0.0014 | 2020-09-13 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-002 | ITP FOR 415V, 250KVA LIGHTING TRANSFORMER | PDF | A | 0.0014 | 2020-09-18 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-003 | ITP FOR 6.6 KV SWITCHGEAR | PDF | A | 0.0014 | 2020-10-11 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-004 | ITP FOR 6.6 KV SOFT STARTER | PDF | A | 0.0014 | 2020-10-11 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-005 | ITP FOR LV PMCC | PDF | A | 0.0014 | 2020-10-08 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-006 | ITP FOR DG SET (3750KVA ) | PDF | A | 0.0014 | 2020-10-13 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-007 | ITP FOR APFC & CAPACITOR BANK | PDF | A | 0.0014 | 2020-08-20 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-008 | ITP FOR LUMINAIRES AND ACCESSORIES | PDF | A | 0.0014 | 2020-09-05 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-009 | ITP FOR LIGHTING AND SMALL POWER PANELS | PDF | A | 0.0014 | 2020-09-25 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-010 | ITP FOR FLAMEPROOF ITEMS (LCS, SW. SOCKETS, JBS ETC.) | PDF | A | 0.0014 | 2020-09-30 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-011 | ITP FOR HIGH MAST | PDF | A | 0.0014 | 2021-01-19 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-012 | ITP FOR HV & LV POWER AND CONTROL CABLES | PDF | A | 0.0014 | 2021-01-11 |  | DUE | 0
ELECTRICAL | VTV-3281-LIT-9511-EL-ITP-013 | ITP FOR ELECTRICAL CABLE TRAY & ACCESSORIES | PDF | A | 0.0014 | 2021-01-29 |  | DUE | 0
EQUIPMENT | VTV-3281-LIT-9511-EQ-CAL-001 | DESIGN CALCULATION FOR COMPRESSOR SUCTION SEPERATORS (B-2304A & B-2304B) | PDF | A | 0.0015 | 2020-08-06 | Rev.01 | IFA | 0.000975 | COMMENTS RECD.ON REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-CAL-002 | DESIGN CALCULATION FOR VENT DRUM (B-2303N) | PDF | A | 0.0015 | 2020-08-02 | REV.01 | IFR | 0.0006 | SUBMITTED REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-CAL-003 | DESIGN CALCULATION FOR DIESEL STORAGE TANK (HSD-T-3002) | PDF | A | 0.0015 | 2020-08-10 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-001 | MECHANICAL DATA SHEET FOR FLASH GAS COMPRESSOR UNIT K-2303-1 A / 2303-2 A & K-2303-1 B / 2303-2 B | PDF | R | 0.0015 | 2020-07-09 | Rev.02 | IFA | 0.000975 | COMMENTS RECD.ON REV.02
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-002 | MATERIAL REQUISITION FOR FLASH GAS COMPRESSOR UNIT K-2303-1 A / 2303-2 A & K-2303-1 B / 2303-2 B | PDF | I | 0.0015 | 2020-07-09 | Rev.02 | IFA | 0.000975 | COMMENTS RECD.ON REV.02
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-004 | PURCHASE REQUISITION FOR FLASH GAS COMPRESSOR UNIT K-2303-1 A / 2303-2 A & K-2303-1 B / 2303-2 B | PDF | A | 0.0015 | 2020-08-18 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-005 | VENDOR DELIVERABLE LIST FOR FLASH GAS COMPRESSOR UNIT K-2303-1 A / 2303-2 A & K-2303-1 B / 2303-2 B | PDF | R | 0.0015 | 2020-08-20 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-006 | MDS FOR COMPRESSOR SUCTION SEPERATORS (B-2304A & B-2304B) | PDF | A | 0.0015 | 2020-08-06 | Rev.01 | IFA | 0.000975 | COMMENTS RECD.ON REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-007 | MDS FOR VENT DRUM (B-2303N) | PDF | A | 0.0015 | 2020-08-02 | REV.01 | IFR | 0.0006 | SUBMITTED REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-008 | MECHANICAL DATA SHEET FOR IN-TANK PROPANE/BUTANE TRANSFER PUMPS (P-4301 A/B/C & P-5301 A/B/C) | PDF | R | 0.0015 | 07-07-2020 | Rev.01 | IFA | 0.000975 | SUBMITTED REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-009 | MATERIAL REQUISITION FOR IN-TANK PROPANE/BUTANE TRANSFER PUMPS (P-4301 A/B/C & P-5301 A/B/C) | PDF | I | 0.0015 | 07-07-2020 | Rev.01 | IFA | 0.000975 | SUBMITTED REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-011 | PURCHASE REQUISITION FOR IN-TANK PROPANE/BUTANE TRANSFER PUMPS (P-4301 A/B/C & P-5301 A/B/C) | PDF | A | 0.0015 | 2020-08-21 | Rev.00 | IFA | 0.000975 | SUBMITTED REV.00
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-012 | VENDOR DELIVERABLE LIST FOR IN-TANK PROPANE/BUTANE TRANSFER PUMPS (P-4301 A/B/C & P-5301 A/B/C) | PDF | R | 0.0015 | 2020-08-28 |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-013 | DATA SHEET FOR JET TYPE COOLING TOWER PACKAGE (CT-3002) | PDF | R | 0.0015 | 2020-07-08 | REV.02 | AFC | 0.001425 | RECD COMMENTS ON REV.02
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-014 | MR FOR JET TYPE COOLING TOWER PACKAGE (CT-3002) | PDF | I | 0.0015 | 2020-07-08 | REV.02 | AFC | 0.001425 | RECD COMMENTS ON REV.02
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-016 | PR FOR JET TYPE COOLING TOWER PACKAGE (CT-3002) | PDF | A | 0.0015 | 2020-08-21 |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-017 | VENDOR DELIVERABLE LIST FOR JET TYPE COOLING TOWER PACKAGE (CT-3002) | PDF | R | 0.0015 | 2020-08-28 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-018 | MECHANICAL DATA SHEET FOR COOLING WATER TRANSFER PUMPS (P-3003A/B/C) | PDF | R | 0.0015 | 2020-07-15 | REV.01 | IFA | 0.000975 | RECD COMMENTS ON REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-019 | MATERIAL REQUISITION FOR COOLING WATER TRANSFER PUMPS (P-3003A/B/C) | PDF | I | 0.0015 | 2020-07-15 | REV.01 | IFA | 0.000975 | RECD COMMENTS ON REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-021 | PURCHASE REQUISITION FOR COOLING WATER TRANSFER PUMPS (P-3003A/B/C) | PDF | A | 0.0015 | 2020-08-16 |  | DUE | 0
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-022 | VENDOR DELIVERABLE LIST FOR COOLING WATER TRANSFER PUMPS (P-3003A/B/C) | PDF | R | 0.0015 | 2020-08-23 |  | DUE | 0
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-023 | MECHANICAL DATA SHEET FOR LP STEAM CONDENSATE PUMPS (P-2309R A/B) | PDF | R | 0.0015 | 2020-07-30 | REV.03 | IFA | 0.000975 | SUBMITTED REV.03
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-024 | MATERIAL REQUISITION FOR LP STEAM CONDENSATE PUMPS (P-2309R A/B) | PDF | I | 0.0015 | 2020-07-30 | REV.03 | IFA | 0.000975 | SUBMITTED REV.03
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-026 | PURCHASE REQUISITION FOR LP STEAM CONDENSATE PUMPS (P-2309R A/B) | PDF | A | 0.0015 | 2020-08-11 |  | DUE | 0
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-027 | VENDOR DELIVERABLE LIST FOR LP STEAM CONDENSATE PUMPS (P-2309R A/B) | PDF | R | 0.0015 | 2020-08-18 |  | DUE | 0
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-028 | MECHANICAL DATA SHEET FOR BLOWDOWN PIT PUMPS (P-3111 A/B) | PDF | R | 0.0015 | 2020-08-10 | REV.01 | IFA | 0.000975 | COMMENTS RECD ON REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-029 | MATERIAL REQUISITION FOR BLOWDOWN PIT PUMPS (P-3111 A/B) | PDF | I | 0.0015 | 2020-08-10 | REV.01 | IFA | 0.000975 | COMMENTS RECD ON REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-031 | PURCHASE REQUISITION FOR BLOWDOWN PIT PUMPS (P-3111 A/B) | PDF | A | 0.0015 | 2020-09-16 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-032 | VENDOR DELIVERABLE LIST FOR BLOWDOWN PIT PUMPS (P-3111 A/B) | PDF | R | 0.0015 | 2020-09-23 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-033 | MR FOR EFFLUENT TREATMENT PLANT | PDF | I | 0.0015 | 2020-08-05 | REV.0 | IFA | 0.000975 | COMMENTS RECD ON REV.0
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-035 | PR FOR EFFLUENT TREATMENT PLANT | PDF | A | 0.0015 | 2020-09-11 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-036 | VENDOR DELIVERABLE LIST FOR EFFLUENT TREATMENT PLANT | PDF | R | 0.0015 | 2020-09-18 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-037 | MECHANICAL DATA SHEET FOR EFFLUENT TRANSFER PUMPS (P-3009A/B) | PDF | R | 0.0015 | 2020-08-05 | REV.01 | IFA | 0.000975 | SUBMITTED REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-038 | MATERIAL REQUISITION FOR EFFLUENT TRANSFER PUMPS (P-3009A/B) | PDF | I | 0.0015 | 2020-08-20 | REV.01 | IFA | 0.000975 | SUBMITTED REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-040 | PURCHASE REQUISITION FOR EFFLUENT TRANSFER PUMPS (P-3009A/B) | PDF | A | 0.0015 | 2020-09-26 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-041 | VENDOR DELIVERABLE LIST FOR EFFLUENT TRANSFER PUMPS (P-3009A/B) | PDF | R | 0.0015 | 2020-09-29 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-042 | MR FOR CHEMICAL DOSING PACKAGE | PDF | I | 0.0015 | 2020-08-10 | REV.01 | IFR | 0.0006 | SUBMITTED REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-044 | VENDOR DOCUMENTS FOR CHEMICAL DOSING PACKAGE | PDF | R | 0.0015 | 2020-09-23 |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-045 | MR FOR ACID DOSING PACKAGE | PDF | I | 0.0015 | 2020-08-04 | REV.0 | IFR | 0.0006 | SUBMITTED REV.0
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-047 | VENDOR DOCUMENTS FOR ACID DOSING PACKAGE | PDF | R | 0.0015 | 2020-09-17 |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-048 | MR FOR CHLORINATOR PACKAGE | PDF | I | 0.0015 | 2020-08-17 | REV.0 | IFR | 0.0006 | SUBMITTED REV.0
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-050 | VENDOR DOCUMENTS FOR CHLORINATOR PACKAGE | PDF | R | 0.0015 | 2020-09-30 |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-051 | MDS FOR DIESEL STORAGE TANK (HSD-T-3002) | PDF | R | 0.0015 | 2020-08-10 |  | IFR | 0.0006 | TO BE COVERED UNDER ELECTRICAL DG SET MR
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-052 | MR FOR EOT CRANE FOR NEW COMPRESSOR HOUSE | PDF | I | 0.0015 | 2020-09-05 | REV.0 | IFA | 0.000975 | COMMENTS RECD ON REV.00
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-053 | TBE FOR EOT CRANE FOR NEW COMPRESSOR HOUSE | PDF | I | 0.0015 |  |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-054 | PR FOR EOT CRANE FOR NEW COMPRESSOR HOUSE | PDF | A | 0.0015 | 2020-10-08 |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-055 | VENDOR DELIVERABLE LIST FOR EOT CRANE | PDF | R | 0.0015 | 2020-10-15 |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-056 | MR FOR ELECTRICAL HOIST FOR TANKS | PDF | I | 0.0015 | 2020-09-05 | REV.02 | IFA | 0.000975 | COMMENTS RECD ON REV.02
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-057 | TBE FOR ELECTRICAL HOIST FOR TANKS | PDF | I | 0.0015 |  |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-058 | PR FOR ELECTRICAL HOIST FOR TANKS | PDF | A | 0.0015 | 2020-10-12 |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-078 | MATERIAL REQUISITION FOR SIDE STREAM FILTER | PDF | I | 0.0015 | 2020-07-14 | REV.01 | IFA | 0.000975 | RETAINED FOR RECORDS
EQUIPMENT | VTV-3281-LIT-9511-EQ-DOC-080 | VENDOR DELIVERABLE LIST FOR SIDE STREAM FILTER | PDF | R | 0.0015 | 2020-08-17 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DRG-001 | GENERAL ARRANGEMENT DRAWING FOR COMPRESSOR SUCTION SEPERATORS (B-2304A & B-2304B) | PDF | R | 0.0015 | 2020-08-16 | Rev.01 | IFA | 0.000975 | COMMENTS RECD.ON REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DRG-002 | FABRICATION DRAWING OF COMPRESSOR SUCTION SEPERATOR (B-2304/A & B-2304/B) | PDF | R | 0.0015 | 2020-08-23 |  | IFR | 0.0006
EQUIPMENT | VTV-3281-LIT-9511-EQ-DRG-003 | GENERAL ARRANGEMENT DRAWING OF VENT DRUM (B-2303N) | PDF | R | 0.0015 | 2020-08-12 | REV.01 | IFR | 0.0006 | SUBMITTED REV.01
EQUIPMENT | VTV-3281-LIT-9511-EQ-DRG-004 | FABRICATION DRAWING OF VENT DRUM (B-2303N) | PDF | R | 0.0015 | 2020-09-01 | REV.00 | IFR | 0.0006 | SUBMITTED REV.00
EQUIPMENT | VTV-3281-LIT-9511-EQ-DRG-005 | GENERAL ARRANGEMENT DRAWING OF DIESEL STORAGE TANK (HSD-T-3002) | PDF | R | 0.0015 | 2020-09-01 |  | IFA | 0.000975
EQUIPMENT | VTV-3281-LIT-9511-EQ-DRG-006 | FABRICATION DRAWING OFDIESEL STORAGE TANK (HSD-T-3002) | PDF | R | 0.0015 | 2020-09-16 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-CAL-001 | FIRE WATER DEMAND CALCULATION NEW FACILITY | PDF | A | 0.0015 | 2020-08-20 | Rev.01 | AFC | 0.001425 | COMMENTS RECD ON REV.01
FIRE PROTECTION | VTV-3281-LIT-9511-FP-CAL-002 | HYDRAULIC CALCULATION- RING MAIN FOR NEW FACILITY | PDF | A | 0.0015 | 2020-09-02 | Rev.0 | IFA | 0.000975 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-CAL-003 | HYDRAULIC CALCULATION- MVWS SYSTEM FOR STORAGE TANK T-4301 & T-5301 | PDF | A | 0.0015 | 2020-09-02 | Rev.0 | IFA | 0.000975 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-CAL-005 | HYDRAULIC CALCULATION- MVWS SYSTEM FOR FLASH GAS COMPRESSORS | PDF | A | 0.0015 | 2020-09-02 | Rev.0 | IFA | 0.000975 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-CAL-006 | HYDRAULIC CALCULATION- MVWS SYSTEM FOR NEW MOUNDED BULLETS | PDF | A | 0.0015 | 2020-09-02 | Rev.0 | IFA | 0.000975 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-001 | DESIGN BASIS FOR FIRE PROTECTION SYSTEM | PDF | A | 0.0015 | 2020-08-15 | REV.0 | AFC | 0.001425 | COMMENTS RECD. ON REV.0
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-002 | FIREWATER NETWORK (RING MAIN FOR NEW FACILITY) SURGE ANALYSIS REPORT | PDF | R | 0.0015 | 2020-08-20 |  | IFR | 0.0006
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-003 | DATASHEET- SPRAY NOZZLE | PDF | R | 0.0015 | 2020-09-22 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-004 | DATASHEET- QBD | PDF | R | 0.0015 | 2020-09-22 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-005 | DATASHEET - RESTRICTION ORIFICE | PDF | R | 0.0015 | 2020-09-22 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-006 | DATASHEET - DELUGE VALVE | PDF | R | 0.0015 | 2020-09-07 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-007 | DATASHEET - FIRE HYDRANT | PDF | R | 0.0015 | 2020-09-07 | REV.02 | IFA | 0.000975 | COMMENTS ON REV.02
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-008 | DATASHEET - FIRE HOSE REEL, NOZZLE & BOX | PDF | R | 0.0015 | 2020-09-07 | REV.01 | IFA | 0.000975 | COMMENTS ON REV.01
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-009 | DATASHEET - FIRE WATER MONITOR | PDF | R | 0.0015 | 2020-09-14 | REV.02 | IFA | 0.000975 | COMMENTS ON REV.02
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-010 | DATA SHEET FOR FIRE EXTINGUISHERS | PDF | R | 0.0015 | 2020-09-14 |  | AFC | 0.001425
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-011 | DATA SHEET FOR EYE WASHER AND SAFETY SHOWER | PDF | R | 0.0015 | 2020-09-14 | REV.01 | AFC | 0.001425 | COMMENTS ON REV.01
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-014 | DATA SHEET FOR HIGH VOLUME LONGE RANGE MONITORS | PDF | R | 0.0015 | 2020-09-14 | REV.01 | AFC | 0.001425 | COMMENTS ON REV.01
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-015 | DATA SHEET FOR PROTECTIVE COATING OF UG LINES | PDF | R | 0.0015 | 2020-09-14 | Rev.0 | AFC | 0.001425 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-016 | VENDOR DOCUMENTS FOR SPRAY NOZZLE | PDF | R | 0.0015 | 2021-01-18 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-017 | VENDOR DOCUMENTS FOR QBD | PDF | R | 0.0015 | 2021-01-18 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-018 | VENDOR DOCUMENTS FOR RESTRICTION ORIFICE | PDF | R | 0.0015 | 2021-01-20 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-019 | VENDOR DOCUMENTS FOR DELUGE VALVE | PDF | R | 0.0015 | 2020-12-28 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-020 | VENDOR DOCUMENTS FOR HYDRANTS | PDF | R | 0.0015 | 2020-12-20 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-021 | VENDOR DOCUMENTS FOR HOSE REEL, HOSE BOX & NOZZLE | PDF | R | 0.0015 | 2021-01-03 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-022 | VENDOR DOCUMENTS FOR MONITORS | PDF | R | 0.0015 | 2021-01-03 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-023 | VENDOR DOCUMENTS FOR HVLR MONITORS | PDF | R | 0.0015 | 2021-01-03 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-024 | VENDOR DOCUMENTS FOR FIRE EXTINGUISHERS | PDF | R | 0.0015 | 2021-04-15 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DOC-025 | VENDOR DOCUMENTS FOR EYE WASHER & SAFETY SHOWER | PDF | R | 0.0015 | 2021-04-15 |  | IFA | 0.000975
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-001 | P&ID - FIREWATER RING MAIN FOR NEW FACILITY | PDF | A | 0.0015 | 2020-08-20 | REV.0 | AFC | 0.001425 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-002 | P&ID - MVWS SYSTEM FOR STORAGE TANK T-4301 | PDF | A | 0.0015 | 2020-08-25 | REV.0 | AFC | 0.001425 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-003 | P&ID - MVWS SYSTEM FOR STORAGE TANK T-5301 | PDF | A | 0.0015 | 2020-08-25 | REV.0 | AFC | 0.001425 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-004 | P&ID - MVWS SYSTEM FOR FLASH GAS COMPRESSORS | PDF | A | 0.0015 | 2020-08-25 | REV.0 | AFC | 0.001425 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-005 | P&ID - MVWS SYSTEM FOR NEW MOUNDED BULLETS | PDF | A | 0.0015 | 2020-08-25 | REV.0 | AFC | 0.001425 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-006 | RING MAIN LAYOUT | PDF | A | 0.0015 | 2020-09-02 | REV.0 | AFC | 0.001425 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-007 | FIREFIGHTING EQUIPMENT LAYOUT | PDF | A | 0.0015 | 2020-09-02 |  | IFR | 0.0006
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-008 | ESCAPE ROUTE LAYOUT | PDF | A | 0.0015 | 2020-09-02 | REV.0 | IFR | 0.0006 | SUBMITTED REV.00
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-010 | FIRE PROOFING LAYOUT | PDF | A | 0.0015 | 2020-09-02 |  | IFR | 0.0006
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-011 | FABRICATION DRAWINGS FOR MVWS SYSTEM - T-4301 & T-5301 | PDF | R | 0.0015 | 2021-03-24 |  | DUE | 0
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-012 | FABRICATION DRAWINGS FOR MVWS SYSTEM - COMPRESSOR AREA | PDF | R | 0.0015 | 2021-03-24 |  | DUE | 0
FIRE PROTECTION | VTV-3281-LIT-9511-FP-DRG-013 | FABRICATION DRAWINGS FOR MVWS SYSTEM - MOUNDED BULLETS | PDF | R | 0.0015 | 2021-03-24 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-001 | INSTRUMENT INDEX | PDF | A | 0.0014 | 2020-08-24 | REV.03 | IFR | 0.00056 | SUBMITTED REV.03
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-002 | INSTRUMENT I / O POINT DATA BASE FOR PLC & DCS | PDF | A | 0.0014 | 2020-08-30 | REV.01 | IFA | 0.00091 | RECD. COMMENTS ON REV.01
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-003 | INSTRUMENTATION CABLE SCHEDULE | PDF | A | 0.0014 | 2020-11-25 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-004 | INSTRUMENTATION LOAD LIST ( UPS AND NON-UPS POWER) | PDF | I | 0.0014 | 2020-09-06 | REV.03 | AFC | 0.00133 | SUBMITTED REV.03
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-005 | PR FOR LEVEL GAUGE (RADAR) | PDF | A | 0.0014 | 2020-10-19 | REV.0 | AFC | 0.00133 | SUBMITTED REV.0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-006 | PR FOR LEVEL GAUGE (SERVO) | PDF | A | 0.0014 | 2020-10-19 | REV.0 | AFC | 0.00133 | SUBMITTED REV.0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-007 | PR FOR LEVEL TRANSMITTER (GWR) | PDF | A | 0.0014 | 2020-10-19 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-010 | PR FOR FLOW INDICATOR | PDF | A | 0.0014 | 2020-11-10 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-011 | PR FOR PRESSURE TRANSMITTER | PDF | A | 0.0014 | 2020-11-16 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-012 | PR FOR PRESSURE GAUGE | PDF | A | 0.0014 | 2020-11-10 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-013 | PR FOR PRESSURE SWITCH | PDF | A | 0.0014 | 2020-12-16 | REV.0 | AFC | 0.00133 | RECD. COMMENTS ON REV.00 DOC NUMBER CHANGED
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-014 | PR FOR TEMPERATURE ELEMENT (MULTIPOINT RTD) | PDF | A | 0.0014 | 2020-12-16 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-015 | PR FOR TEMPERATURE ELEMENT (RTD) | PDF | A | 0.0014 | 2020-12-12 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-016 | PR FOR TEMPERATURE GAUGE | PDF | A | 0.0014 | 2020-12-12 | REV.0 | AFC | 0.00133 | SUBMITTED REV.0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-017 | PR FOR TEMPERATURE TRANSMITTER | PDF | A | 0.0014 | 2021-01-16 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-019 | PR FOR ANALYZER | PDF | A | 0.0014 | 2020-12-30 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-020 | PR FOR CONTROL VALVES | PDF | A | 0.0014 | 2020-11-22 | REV.0 | AFC | 0.00133 | SUBMITTED REV.0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-021 | PR FOR ON-OFF VALVES | PDF | A | 0.0014 | 2020-11-19 | REV.0 | AFC | 0.00133 | SUBMITTED REV.0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-022 | PR FOR JUNCTION BOXES | PDF | A | 0.0014 | 2021-02-19 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-023 | PR FOR FIRE ALARM | PDF | A | 0.0014 | 2021-03-29 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-024 | PR FOR INSTRUMENTATION CABLES | PDF | A | 0.0014 | 2021-05-09 |  | IFA | 0.00091
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-025 | PR FOR CABLE TRAYS AND ACCESSORIES | PDF | A | 0.0014 | 2021-05-19 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-026 | INSTRUMENT BULK MATERIAL (MTO) | PDF | A | 0.0014 | 2021-07-16 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-027 | MANDATORY SPARE LIST FOR INSTRUMENT ITEMS | PDF | I | 0.0014 | 2021-06-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-028 | SIL STUDY REPORT | PDF | I | 0.0014 | 2021-01-20 |  | IDC | 0.00021
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-029 | MATERIAL REQUISITION FOR VIBRATION & CONDITIONING MONITORING SYSTEM (VCMS) | PDF | I | 0.0014 |  | REV.01 | AFC | 0.00133 | Submitted REV.01
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /01 | SYSTEM DATA SHEET AND SPECIFICATION | PDF | R | 0.0014 | 2020-11-15 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /02 | HARDWARE DESIGN MANUAL | PDF | A | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /03 | POWER CONSUMPTION LIST AND UPS REQUIREMENT | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /04 | LOOP WIRING DIAGRAM | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /05 | POWER DISTRIBUTION SCHEME | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /06 | I/O ALLOCATION DETAILS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /07 | LOGIC/LADDER DIAGRAM OF PLC | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /08 | GRAPHIC DISPLAY DRAWINGS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /09 | BILL OF MATERIAL & SOFTWARE DETAILS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /10 | GA-IA DRAWING | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /11 | SYSTEM LOADING DETAILS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /12 | SYSTEM GROUNDING DETAILS & CALCULATION | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /13 | OVERVIEW, GROUP VIEW REQUIREMENT | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /14 | GRAPHIC DISPLAY, LOG AND MIS PRINTOUTS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /15 | LOGGING AND LOG FORMATS REQUIREMENTS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /16 | TRENDING AND TREND GROUPING REQUIREMENTS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /17 | MTBF & MTTR DETAILS, SYSTEM AVAILABILITY DETAILS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /18 | SPECIAL SOFTWARE DETAILS INCLUDING THIRD PARTY INTERFACE | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /19 | BUS LOADING CALCULATIONS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /20 | SYSTEM ARCHITECTURE DRAWING | PDF | A | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /21 | SYSTEM CONFIGURATION AND PROGRAMMING MANUALS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /22 | FIELD TERMINATION DETAILS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /23 | INSTALLATION DETAILS AND OPERATING & MAINTENANCE MANUALS | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /24 | FAT PROCEDURE / REPORT | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /25 | SAT PROCEDURE / REPORT | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-030 /26 | FINAL DOCUMENTS IN CD / DVD | PDF | I | 0.0014 | 2020-12-15 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-031 | LOOP CHECKING REPORT | PDF | I | 0.0014 | 2022-03-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-032 | FIT-UP REPORT | PDF | I | 0.0014 | 2022-03-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-033 | INSTRUMENTATION ERECTION REPORT | PDF | I | 0.0014 | 2022-03-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-034 | SYSTEM ERECTION REPORT | PDF | I | 0.0014 | 2022-03-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-035 | CABLE / TRAY ERECTION REPORT | PDF | I | 0.0014 | 2022-03-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-036 | COMMISSIONING REPORT | PDF | I | 0.0014 | 2022-03-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-037 | EARTH PIT DETAILS | PDF | I | 0.0014 | 2022-03-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-038 | CONTROL ROOM / PANEL FOUNDATION DETAILS (CHANNEL BASE DRAWINGS) | PDF | I | 0.0014 | 2022-03-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-039 | CALIBRATION REPORT | PDF | I | 0.0014 | 2022-03-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-040 | MR FOR FLOW INDICATOR |  |  | 0.0014 |  | REV.0 | AFC | 0.00133 | Submitted REV.0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-042 | MR FOR PRESSURE GAUGE |  |  | 0.0014 |  | REV.0 | AFC | 0.00133 | Submitted REV.0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DOC-044 | MR FOR TEMPERATURE TRANSMITTER |  |  | 0.0014 |  | REV.0 | AFC | 0.00133 | Submitted REV.0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-001 | EQUIPMENT LAYOUT - CONTROL ROOM EXTENSION | PDF | A | 0.0014 | 2020-10-06 | REV.01 | AFC | 0.00133 | commts recd on Rev.01
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-002 | INSTRUMENT CABLE BLOCK DIAGRAMS | PDF | R | 0.0014 | 2020-10-21 | REV.0 | AFC | 0.00133 | commts recd on Rev.00
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-003 | INSTRUMENT & JB LOCATION LAYOUT | PDF | A | 0.0014 | 2020-10-14 | REV.0 | AFC | 0.00133 | commts recd on Rev.00
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-004 | INSTRUMENT CABLE / TRAY ROUTING LAYOUT | PDF | A | 0.0014 | 2020-12-15 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-005 | INSTRUMENT JB WIRING DIAGRAMS | PDF | R | 0.0014 | 2020-11-15 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-006 | INSTRUMENT HOOKUP DRAWINGS | PDF | R | 0.0014 | 2020-12-05 |  | IFA | 0.00091
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-007 | INSTRUMENT LOOP DIAGRAMS | PDF | R | 0.0014 | 2020-12-30 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-008 | INSTRUMENT LOGIC DIAGRAM | PDF | I | 0.0014 | 2020-12-04 |  | IFA | 0.00091
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-009 | WIRING & INTERCONNECTION DIAGRAMS | PDF | R | 0.0014 | 2021-02-04 |  | IFA | 0.00091
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-010 | LEVEL SKETCHES / NOZZLE ELEVATIONS FOR LEVEL | PDF | I | 0.0014 | 2020-10-20 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-011 | FIRE & GAS DETECTOR LOCATION LAYOUT | PDF | A | 0.0014 | 2020-12-15 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-012 | TANK GAUGING SYSTEM ARCHITECTURE DRAWING | PDF | R | 0.0014 | 2020-09-15 | REV.02 | AFC | 0.00133 | SUBMITTED REV.02
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-013 | FIRE ALARM SYSTEM LAYOUT | PDF | A | 0.0014 | 2020-10-25 |  | AFC | 0.00133
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-014 | VENDOR DRAWINGS - PILOT PSV | PDF | A | 0.0014 | 2021-01-28 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-015 | VENDOR DRAWINGS - PSV / TSV | PDF | A | 0.0014 | 2021-04-16 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-016 | VENDOR DRAWINGS - VRV | PDF | A | 0.0014 | 2021-01-28 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-DRG-017 | VENDOR DRAWINGS - SELF ACTUATED PCV | PDF | A | 0.0014 | 2021-01-28 |  | IFR | 0.00056
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-001 | ITP FOR LEVEL GAUGE (RADAR) | PDF | A | 0.0014 | 2020-10-19 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-002 | ITP FOR LEVEL GAUGE (SERVO) | PDF | A | 0.0014 | 2020-10-19 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-003 | ITP FOR LEVEL TRANSMITTER (GWR) | PDF | A | 0.0014 | 2020-10-19 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-004 | ITP FOR FLOW ELEMENT | PDF | A | 0.0014 | 2020-10-08 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-005 | ITP FOR FLOW TRANSMITTER | PDF | A | 0.0014 | 2020-10-08 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-006 | ITP FOR FLOW INDICATOR | PDF | A | 0.0014 | 2020-11-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-007 | ITP FOR PRESSURE TRANSMITTER | PDF | A | 0.0014 | 2020-11-16 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-008 | ITP FOR PRESSURE GAUGE | PDF | A | 0.0014 | 2020-11-10 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-009 | ITP FOR PRESSURE SWITCH | PDF | A | 0.0014 | 2020-12-16 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-010 | ITP FOR TEMPERATURE ELEMENT (MULTIPOINT RTD) | PDF | A | 0.0014 | 2020-12-16 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-011 | ITP FOR TEMPERATURE ELEMENT (RTD) | PDF | A | 0.0014 | 2020-12-12 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-012 | ITP FOR TEMPERATURE GAUGE | PDF | A | 0.0014 | 2020-12-12 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-013 | ITP FOR TEMPERATURE TRANSMITTER | PDF | A | 0.0014 | 2021-01-16 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-014 | ITP FOR GAS / FLAME DETECTORS | PDF | A | 0.0014 | 2020-12-16 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-015 | ITP FOR ANALYZER | PDF | A | 0.0014 | 2020-12-30 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-016 | ITP FOR CONTROL VALVES | PDF | A | 0.0014 | 2020-11-22 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-017 | ITP FOR ON-OFF VALVES | PDF | A | 0.0014 | 2020-11-19 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-018 | ITP FOR JUNCTION BOXES | PDF | A | 0.0014 | 2021-02-19 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-019 | ITP FOR INSTRUMENTATION CABLES | PDF | A | 0.0014 | 2021-03-29 |  | DUE | 0
INSTRUMENTATION | VTV-3281-LIT-9511-IN-ITP-020 | ITP FOR CABLE TRAYS AND ACCESSORIES | PDF | A | 0.0014 | 2021-03-29 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-001 | ISOMETRIC INDEX | PDF | I | 0.0014 | 2021-05-30 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-002 | PIPING MATERIAL SPECIFICATION (PMS) | PDF | R | 0.0014 | 03-07-2020 | REV.02 | AFC | 0.00133 | submitted REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-003 | VALVE MATERIAL SPECIFICATION (VMS) | PDF | R | 0.0014 | 05-07-2020 | REV.02 | AFC | 0.00133 | submitted REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-004 | STRESS CRITICAL LINE LIST | PDF | A | 0.0014 | 2020-07-15 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DOC-005 | STRESS ANALYSIS REPORT - SYSTEM 1 | PDF | R | 0.0014 | 2020-10-12 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-006 | STRESS ANALYSIS REPORT - SYSTEM 2 | PDF | R | 0.0014 | 2020-10-14 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DOC-007 | STRESS ANALYSIS REPORT - SYSTEM 3 | PDF | R | 0.0014 | 2020-10-17 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-008 | STRESS ANALYSIS REPORT - SYSTEM 4 | PDF | R | 0.0014 | 2020-10-19 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-009 | STRESS ANALYSIS REPORT - SYSTEM 5 | PDF | R | 0.0014 | 2020-10-21 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-010 | STRESS ANALYSIS REPORT - SYSTEM 6 | PDF | R | 0.0014 | 2020-10-24 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-011 | STRESS ANALYSIS REPORT - SYSTEM 7 | PDF | R | 0.0014 | 2020-11-02 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-012 | STRESS ANALYSIS REPORT - SYSTEM 8 | PDF | R | 0.0014 | 2020-11-02 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-013 | STRESS ANALYSIS REPORT - SYSTEM 9 | PDF | R | 0.0014 | 2020-11-02 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DOC-014 | STRESS ANALYSIS REPORT - SYSTEM 10 | PDF | R | 0.0014 | 2020-11-04 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-015 | STRESS ANALYSIS REPORT - SYSTEM 11 | PDF | R | 0.0014 | 2020-11-07 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-016 | STRESS ANALYSIS REPORT - SYSTEM 12 | PDF | R | 0.0014 | 2020-11-09 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-017 | PIPING BULK MTO | PDF | I | 0.0014 | 2021-05-15 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DOC-018 | SPECIFICATION FOR PIPING & EQUIPMENT INSULATION | PDF | R | 0.0014 | 2020-12-03 | REV.0 | IFA | 0.00091 | Submitted REV.00
PIPING | VTV-3281-LIT-9511-PP-DOC-019 | TECHNICAL SPECIFICATION FOR CS PIPES | PDF | R | 0.0014 | 2020-08-03 | REV.03 | AFC | 0.00133 | RECD COMMENTS ON REV.03
PIPING | VTV-3281-LIT-9511-PP-DOC-020 | TECHNICAL SPECIFICATION FOR LTCS PIPES | PDF | R | 0.0014 | 2020-08-03 | REV.01 | AFC | 0.00133 | Submitted REV.01
PIPING | VTV-3281-LIT-9511-PP-DOC-021 | TECHNICAL SPECIFICATION FOR SS PIPES | PDF | R | 0.0014 | 2020-08-04 | REV.01 | AFC | 0.00133 | Submitted REV.01
PIPING | VTV-3281-LIT-9511-PP-DOC-022 | TECHNICAL SPECIFICATION FOR CS FITTINGS | PDF | R | 0.0014 | 2020-08-04 | REV.01 | AFC | 0.00133 | COMMENTS RECD ON REV.01
PIPING | VTV-3281-LIT-9511-PP-DOC-023 | TECHNICAL SPECIFICATION FOR LTCS FITTINGS | PDF | R | 0.0014 | 2020-08-05 | REV.01 | AFC | 0.00133 | Submitted REV.01
PIPING | VTV-3281-LIT-9511-PP-DOC-024 | TECHNICAL SPECIFICATION FOR SS FITTINGS | PDF | R | 0.0014 | 2020-08-05 | REV.01 | AFC | 0.00133 | COMMENTS RECD ON REV.01
PIPING | VTV-3281-LIT-9511-PP-DOC-025 | TECHNICAL SPECIFICATION FOR CS FLANGES | PDF | R | 0.0014 | 2020-08-06 | REV.02 | AFC | 0.00133 | COMMENTS RECD ON REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-026 | TECHNICAL SPECIFICATION FOR LTCS FLANGES | PDF | R | 0.0014 | 2020-08-06 | REV.02 | AFC | 0.00133 | COMMENTS RECD ON REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-027 | TECHNICAL SPECIFICATION FOR SS FLANGES | PDF | R | 0.0014 | 2020-08-07 | REV.02 | AFC | 0.00133 | COMMENTS RECD ON REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-028 | TECHNICAL SPECIFICATION FOR CS FASTENERS | PDF | R | 0.0014 | 2020-08-07 | REV.02 | AFC | 0.00133 | COMMENTS RECD ON REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-029 | TECHNICAL SPECIFICATION FOR LTCS FASTENERS | PDF | R | 0.0014 | 2020-08-08 | REV.02 | AFC | 0.00133 | COMMENTS RECD ON REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-030 | TECHNICAL SPECIFICATION FOR SS FASTENERS | PDF | R | 0.0014 | 2020-08-08 | REV.02 | AFC | 0.00133 | COMMENTS RECD ON REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-031 | TECHNICAL SPECIFICATION FOR GASKETS | PDF | R | 0.0014 | 2020-08-10 | REV.02 | AFC | 0.00133 | Submitted Rev.02
PIPING | VTV-3281-LIT-9511-PP-DOC-032 | TECHNICAL SPECIFICATION FOR BALL VALVES | PDF | R | 0.0014 | 2020-08-10 | REV.01 | AFC | 0.00133 | Submitted Rev.01
PIPING | VTV-3281-LIT-9511-PP-DOC-033 | TECHNICAL SPECIFICATION FOR GATE VALVES | PDF | R | 0.0014 | 2020-08-11 | REV.02 | AFC | 0.00133 | Submitted Rev.02
PIPING | VTV-3281-LIT-9511-PP-DOC-034 | TECHNICAL SPECIFICATION FOR BUTTERFLY VALVES | PDF | R | 0.0014 | 2020-08-11 | REV.02 | AFC | 0.00133 | Submitted Rev.02
PIPING | VTV-3281-LIT-9511-PP-DOC-035 | TECHNICAL SPECIFICATION FOR CHECK VALVES | PDF | R | 0.0014 | 2020-08-12 | REV.02 | AFC | 0.00133 | SUBMITTED REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-036 | TECHNICAL SPECIFICATION FOR GLOBE VALVES | PDF | R | 0.0014 | 2020-08-12 | REV.02 | AFC | 0.00133 | SUBMITTED REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-037 | TECHNICAL SPECIFICATION FOR STRAINERS | PDF | R | 0.0014 | 2020-08-13 | REV.01 | AFC | 0.00133 | COMMENTS RECD ON REV.01
PIPING | VTV-3281-LIT-9511-PP-DOC-038 | TECHNICAL SPECIFICATION FOR STEAM TRAPS | PDF | R | 0.0014 | 2020-08-13 | REV.01 | AFC | 0.00133 | COMMENTS RECD ON REV.01
PIPING | VTV-3281-LIT-9511-PP-DOC-039 | IBR PACKAGE | PDF | A | 0.0014 | 2020-10-22 |  | IFA | 0.00091
PIPING | VTV-3281-LIT-9511-PP-DOC-040 | 30% 3D MODEL REVIEW | NAVIS | R | 0.0014 | 2020-09-30 |  | AFC | 0.00133
PIPING | VTV-3281-LIT-9511-PP-DOC-041 | 60% 3D MODEL REVIEW | NAVIS | R | 0.0014 | 2021-02-03 |  | IFC | 0.00112
PIPING | VTV-3281-LIT-9511-PP-DOC-042 | 90% 3D MODEL REVIEW | NAVIS | R | 0.0014 | 2021-04-27 |  | IDC | 0.00021
PIPING | VTV-3281-LIT-9511-PP-DOC-043 | FINAL 3D MODEL REVIEW | NAVIS + BD | R | 0.0014 | 2021-05-27 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-044 | PIPE SUPPORT STANDARD | PDF | R | 0.0014 | 2020-10-20 | REV.0 | IFA | 0.00091 | RECD. COMMENTS ON REV.0
PIPING | VTV-3281-LIT-9511-PP-DOC-045 | SPECIFICATION FOR SPRING SUPPORTS | PDF | R | 0.0014 | 2020-10-22 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-046 | SPECIFICATION FOR SPECIAL SUPPORTS | PDF | R | 0.0014 | 2020-10-22 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DOC-047 | MR FOR PILOT OPERATED PSVS | PDF | I | 0.0014 | 2020-08-10 | REV.0 | IFA | 0.00091 | Submitted REV.0
PIPING | VTV-3281-LIT-9511-PP-DOC-048 | MR FOR VACUUM REVIEF VALVES | PDF | I | 0.0014 | 2020-08-16 | REV.0 | IFA | 0.00091 | Submitted REV.0
PIPING | VTV-3281-LIT-9511-PP-DOC-049 | MR FOR SAFETY RELIEF VALVES (PSV/TSV) | PDF | I | 0.0014 | 2020-08-18 | REV.0 | IFA | 0.00091 | COMMENTS RECD. ON REV.0
PIPING | VTV-3281-LIT-9511-PP-DOC-050 | MR FOR SELF ACTUATED PCV | PDF | I | 0.0014 | 2020-09-03 |  | IFA | 0.00091
PIPING | VTV-3281-LIT-9511-PP-DOC-051 | DATASHEET FOR UTILITY HOSE WITH END COUPLING | PDF | R | 0.0014 | 2020-09-29 | REV.0 | IFR | 0.00056 | Submitted REV.0
PIPING | VTV-3281-LIT-9511-PP-DOC-052 | BOLT TENSIONING SPECIFICATION | PDF | R | 0.0014 | 2020-10-12 | REV.01 | AFC | 0.00133 | Submitted REV.01
PIPING | VTV-3281-LIT-9511-PP-DOC-053 | PIPE STRESS DESIGN BASIS | PDF | A | 0.0014 | 2020-07-22 | REV.0 | AFC | 0.00133 | COMMENTS RECD. ON REV.0
PIPING | VTV-3281-LIT-9511-PP-DOC-054 | PRE-ENGINEERING SURVEY REPORT | PDF | I | 0.0014 | 2020-08-02 | REV.0 | AFC | 0.00133 | SUBMITTED REV.00
PIPING | VTV-3281-LIT-9511-PP-DOC-055 | PIPE THICKNESS CALCULATION | PDF | A | 0.0014 | 2020-07-03 | REV.02 | IFA | 0.00091 | SUBMITTED REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-056 | EXECUTION PLAN FOR 3D MODELING. | PDF | I | 0.0014 | 2020-07-03 | REV.02 | AFC | 0.00133 | COMMENTS RECD. ON REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-057 | MODEL REVIEW PROCEDURE (NAVISWORKS / SMART PLANT REVIEW) | PDF | I | 0.0014 | 2020-07-03 | REV.01 | AFC | 0.00133 | COMMENTS RECD. ON REV.01
PIPING | VTV-3281-LIT-9511-PP-DOC-058 | CLASH DETECTION PROCEDURE | PDF | I | 0.0014 | 2020-07-25 | REV.02 | AFC | 0.00133 | COMMENTS RECD. ON REV.02
PIPING | VTV-3281-LIT-9511-PP-DOC-059 | PIPE SUPPORT MTO | PDF | I | 0.0014 | 2021-06-25 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-001 | PLOT PLAN | PDF | A | 0.0014 | 2020-07-15 | REV.02 | IFA | 0.00091 | COMMENTS RECD ON REV.02
PIPING | VTV-3281-LIT-9511-PP-DRG-002 | KEYPLAN AND AREA DIVISION DRAWING | PDF | A | 0.0014 | 2020-07-15 |  | IFA | 0.00091
PIPING | VTV-3281-LIT-9511-PP-DRG-003 | EQUIPMENT LAYOUT - PROPANE & BUTANE STORAGE AREA | PDF | A | 0.0014 | 2020-10-12 |  | IFA | 0.00091
PIPING | VTV-3281-LIT-9511-PP-DRG-004 | EQUIPMENT LAYOUT - FLASH GAS COMPRESSOR AREA | PDF | A | 0.0014 | 2020-10-16 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-005 | EQUIPMENT LAYOUT - UTILITIES & OFFSITES | PDF | A | 0.0014 | 2020-10-20 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-006 | EQUIPMENT LAYOUT - ETP AREA | PDF | A | 0.0014 | 2020-10-19 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-007 | NOZZLE ORIENTATION PROPANE/BUTANE TANK | PDF | R | 0.0014 | 2020-09-26 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-008 | NOZZLE ORIENTATION DIESEL TANK | PDF | R | 0.0014 | 2020-09-27 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-009 | NOZZLE ORIENTATION COMPRESSOR SUCTION SEPARATOR | PDF | R | 0.0014 | 2020-09-30 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-010 | NOZZLE ORIENTATION VENT DRUM | PDF | R | 0.0014 | 2020-09-28 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-011 | PIPING GA DRAWINGS - PROPANE & BUTANE STORAGE AREA | PDF | R | 0.0014 | 2021-04-05 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-012 | PIPING GA DRAWING - MOUNDED STORAGE VESSEL AREA(TILL TIE-IN LIMIT) | PDF | R | 0.0014 | 2021-04-07 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-013 | PIPING GA DRAWING - FLASH GAS COMPRESSOR AREA | PDF | R | 0.0014 | 2021-04-10 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-014 | PIPING GA DRAWING - UTILITIES & OFFSITES | PDF | R | 0.0014 | 2021-04-10 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-015 | PIPING GA DRAWING- ETP AREA(TILL TIE-IN LIMIT) | PDF | R | 0.0014 | 2021-04-10 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-016 | PIPING GA DRAWING - LP-BOILER AREA(TILL TIE-IN LIMIT) | PDF | R | 0.0014 | 2021-04-10 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-017 | BATTERY LIMIT TIE-IN DRAWINGS | PDF | R | 0.0014 | 2021-04-25 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-018 | UG PIPING LAYOUT | PDF | R | 0.0014 | 2021-04-30 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-019 | ISOMETRICS LOT-1 | PDF | I | 0.0014 | 2021-03-20 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-020 | ISOMETRICS LOT-2 | PDF | I | 0.0014 | 2021-03-30 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-021 | ISOMETRICS LOT-3 | PDF | I | 0.0014 | 2021-04-10 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-022 | ISOMETRICS LOT-4 | PDF | I | 0.0014 | 2021-04-20 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-023 | ISOMETRICS LOT-5 | PDF | I | 0.0014 | 2021-04-30 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-024 | ISOMETRICS LOT-6 | PDF | I | 0.0014 | 2021-05-30 |  | DUE | 0
PIPING | VTV-3281-LIT-9511-PP-DRG-025 | VENDOR DRAWINGS - BALL VALVE | PDF | A | 0.0014 | 2021-04-25 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-026 | VENDOR DRAWINGS - GATE VALVE | PDF | A | 0.0014 | 2021-04-28 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-027 | VENDOR DRAWINGS - BUTTERFLY VALVE | PDF | A | 0.0014 | 2021-04-30 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-028 | VENDOR DRAWINGS - GLOBE VALVE | PDF | A | 0.0014 | 2021-04-28 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-029 | VENDOR DRAWINGS - CHECK VALVE | PDF | A | 0.0014 | 2021-04-28 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-030 | VENDOR DRAWINGS - STRAINER | PDF | A | 0.0014 | 2021-03-28 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-031 | VENDOR DRAWINGS - STEAM TRAP | PDF | A | 0.0014 | 2021-03-28 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-032 | VENDOR DRAWINGS - SPRING SUPPORT | PDF | A | 0.0014 | 2021-05-28 |  | IFR | 0.00056
PIPING | VTV-3281-LIT-9511-PP-DRG-033 | VENDOR DRAWINGS - SPECIAL SUPPORT | PDF | A | 0.0014 | 2021-06-16 |  | IFR | 0.00056
PROCESS | VTV-3281-LIT-9511-PR-CAL-001 | CONTROL VALVE SIZING CALCULATION REPORT-PROPANE/BUTANE/LPG LIQUID LINE) | PDF | A | 0.0015 | 2020-07-07 | Rev.0 | IFR | 0.0006 | SPLITTED THE CONTROL VALVE SIZING CALCULATION IN LIQUID AND VAPOUR LINE
PROCESS | VTV-3281-LIT-9511-PR-CAL-002 | HYDRAULIC CALCULATION REPORT - PROPANE / BUTANE /LPG VAPOUR LINE | PDF | A | 0.0015 | 2020-07-10 | Rev.0 | AFC | 0.001425 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-003 | HYDRAULIC CALCULATION REPORT -FLARE HEADER UPTO TIE-IN POINT | PDF | A | 0.0015 | 2020-07-15 | Rev.0 | IFR | 0.0006 | SUBMITTED Rev.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-004 | HYDRAULIC CALCULATION REPORT - COOLING WATER SUPPLY / RETURN LINE | PDF | A | 0.0015 | 2020-07-27 | Rev.01 | AFC | 0.001425 | RECD COMMENTS ON REV.01
PROCESS | VTV-3281-LIT-9511-PR-CAL-005 | HYDRAULIC CALCULATION REPORT - WATER SUPPLY LINE | PDF | A | 0.0015 | 2020-08-02 | Rev.0 | AFC | 0.001425 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-006 | HYDRAULIC CALCULATION REPORT - LP STEAM CONDENSATE PUMPS | PDF | A | 0.0015 | 2020-08-04 | Rev.01 | IFR | 0.0006 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-007 | HYDRAULIC CALCULATION REPORT - N2 GAS SUPPLY LINE | PDF | A | 0.0015 | 2020-08-06 |  | AFC | 0.001425
PROCESS | VTV-3281-LIT-9511-PR-CAL-008 | HYDRAULIC CALCULATION REPORT - INSTRUMENT AIR (IA) SUPPLY LINE | PDF | A | 0.0015 | 2020-07-28 |  | AFC | 0.001425
PROCESS | VTV-3281-LIT-9511-PR-CAL-009 | PRESSURE RELIEF VALVE SIZING CALCULATION- PILOT OPERATED VALVE FOR T-4301 & T-5301 | PDF | A | 0.0015 | 2020-07-17 | Rev.03 | AFC | 0.001425 | RECD COMMENTS ON REV.03
PROCESS | VTV-3281-LIT-9511-PR-CAL-010 | VACUUM RELIEF VALVE SIZING CALCULATION FOR T-4301 & T-5301 | PDF | A | 0.0015 | 2020-07-12 | Rev.0 | AFC | 0.001425 | SUBMITTED Rev.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-011 | PRESSURE SAFETY VALVE SIZING CALCULATION- EQUIPMENTS | PDF | A | 0.0015 | 2020-08-10 | Rev.01 | AFC | 0.001425 | RECD COMMENTS ON REV.01
PROCESS | VTV-3281-LIT-9511-PR-CAL-012 | THERMAL RELIEF VALVE SIZING CALCULATION- PROPANE/BUTANE TRANSFER LINE | PDF | A | 0.0015 | 2020-08-12 | Rev.01 | AFC | 0.001425 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-013 | CONTROL VALVE SIZING CALCULATION REPORT- PROPANE / BUTANE /LPG VAPOUR LINE | PDF | A | 0.0015 | 2021-01-28 | Rev.0 | IFR | 0.0006 | SUBMITTED Rev.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-014 | UTILITY DEMAND CALCULATION- NEW FACILITY | PDF | A | 0.0015 | 2020-08-22 | Rev.0 | IFR | 0.0006 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-015 | BLOWDOWN CALCULATION- NEW FACILITY | PDF | A | 0.0015 | 2020-08-20 | Rev.0 | IFR | 0.0006 | SUBMITTED Rev.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-016 | FLARE LOAD CALCULATION- NEW FACILITY | PDF | A | 0.0015 | 2020-08-10 | Rev.0 | IFA | 0.000975 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-017 | HYDRAULIC CALCULATION REPORT - PROPANE / BUTANE TRANSFER PUMPS | PDF | A | 0.0015 | 2020-07-25 | Rev.0 | IFR | 0.0006 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-CAL-018 | BOIL-OFF GAS/VAPOUR LOAD CALCULATION FOR T-4301 AND T-5301 | PDF | A | 0.0015 | 2020-07-26 |  | DUE | 0
PROCESS | VTV-3281-LIT-9511-PR-CAL-019 | COOL DOWN CALCULATION FOR T-4301 AND T-5301 | PDF | A | 0.0015 | 2020-09-03 |  | DUE | 0
PROCESS | VTV-3281-LIT-9511-PR-DOC-001 | SIMULATION STUDY REPORT | PDF | I | 0.0015 | 2020-07-07 | Rev.04 | AFC | 0.001425 | SUBMITTED REV.04
PROCESS | VTV-3281-LIT-9511-PR-DOC-002 | HAZARDOUS AREA CLASSIFICATION SCHEDULE | PDF | A | 0.0015 | 2020-08-05 | Rev.0 | IFA | 0.000975 | RECD COMMENTS ON REV.00
PROCESS | VTV-3281-LIT-9511-PR-DOC-003 | PROCESS CONTROL & INTERLOCK DESCRIPTION | PDF | A | 0.0015 | 2020-07-10 | Rev.0 | IFR | 0.0006 | SUBMITTED
PROCESS | VTV-3281-LIT-9511-PR-DOC-005 | EQUIPMENT LIST | PDF | R | 0.0014 | 12-07-2020 | REV.01 | IFA | 0.00091 | RECD COMMENTS ON REV.01
PROCESS | VTV-3281-LIT-9511-PR-DOC-006 | UTILITY CONSUMPTION LIST | PDF | R | 0.0014 | 2020-09-25 | REV.0 | IFA | 0.00091 | RECD COMMENTS ON REV.00
PROCESS | VTV-3281-LIT-9511-PR-DOC-007 | LINE LIST | PDF | R | 0.0014 | 2020-07-15 | Rev.0 | IFA | 0.00091 | RECD COMMENTS ON REV.00
PROCESS | VTV-3281-LIT-9511-PR-DOC-008 | RELIEF AND BLOWDOWN SUMMARY | PDF | R | 0.0014 | 2020-10-10 |  | DUE | 0
PROCESS | VTV-3281-LIT-9511-PR-DOC-009 | CAUSE & EFFECT MATRIX | PDF | A | 0.0014 | 2020-08-20 | REV.0 | IFR | 0.00056 | RECD COMMENTS ON REV.00
PROCESS | VTV-3281-LIT-9511-PR-DOC-010 | DATASHEET FOR PILOT OPERATED PSV (T-4301 & T-5301) | PDF | R | 0.0015 | 2020-07-17 | Rev.03 | AFC | 0.001425 | RECD COMMENTS ON REV.03
PROCESS | VTV-3281-LIT-9511-PR-DOC-011 | DATASHEET FOR PRESSURE RELIEF/SAFETY VALVES | PDF | R | 0.0015 | 2020-08-11 | REV.0 | AFC | 0.001425 | RECD COMMENTS ON REV.00
PROCESS | VTV-3281-LIT-9511-PR-DOC-012 | DATASHEET FOR VACUUM RELIEF VALVE (T-4301 & T-5301) | PDF | R | 0.0015 | 2020-07-12 | Rev.01 | AFC | 0.001425 | SUBMITTED REV.01
PROCESS | VTV-3281-LIT-9511-PR-DOC-013 | DATASHEET FOR THERMAL RELIEF VALVES | PDF | R | 0.0015 | 2020-07-13 | Rev.0 | AFC | 0.001425 | SUBMITTED
PROCESS | VTV-3281-LIT-9511-PR-DOC-015 | PRE-COMMISSIONING & COMMISSIONING PROCEDURE | PDF | R | 0.0015 | 2021-08-18 |  | DUE | 0
PROCESS | VTV-3281-LIT-9511-PR-DOC-016 | OPERATING MANUAL FULL AUGMENTED PLANT | PDF | R | 0.0015 | 2021-08-18 |  | DUE | 0
PROCESS | VTV-3281-LIT-9511-PR-DOC-017 | HAZOP STUDY REPORT | PDF | A | 0.0015 | 2021-01-10 |  | DUE | 0
PROCESS | VTV-3281-LIT-9511-PR-DOC-019 | PGTR (PERFORMANCE GUARANTEE TEST REPORT) PROCEDURE | PDF | R | 0.0015 | 2021-08-25 |  | DUE | 0
PROCESS | VTV-3281-LIT-9511-PR-DOC-020 | PROCESS DESIGN BASIS | PDF | I | 0.0015 | 2020-07-07 | Rev.02 | AFC | 0.001425 | SUBMITTED Rev.02
PROCESS | VTV-3281-LIT-9511-PR-DOC-021 | SURGE ANALYSIS FOR NEW IN-TANK PUMP (P-4301A/B/C / P-5301 A/B/C) DISCHARGE HEADER TO HEATERS, TLF, RWL & P/LPRE-COOLING OF C/C P/L | PDF | R | 0.0015 | 2020-09-29 |  | DUE | 0
PROCESS | VTV-3281-LIT-9511-PR-DOC-022 | PROCESS PHILOSOPHY | PDF | A | 0.0015 | 2020-07-15 | Rev.01 | AFC | 0.001425 | SUBMITTED Rev.01
PROCESS | VTV-3281-LIT-9511-PR-DOC-023 | TAPPING LIST | PDF | R | 0.0014 | 2020-08-10 |  | AFC | 0.00133
PROCESS | VTV-3281-LIT-9511-PR-DOC-024 | EFFLUENT SUMMARY | PDF | R | 0.0014 | 2020-12-14 | Rev.0 | AFC | 0.00133 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-DOC-025 | QRA REPORT | PDF | I | 0.0014 | 2020-07-25 |  | DUE | 0
PROCESS | VTV-3281-LIT-9511-PR-DOC-026 | HMB FOR LPG IMPORT, STORAGE & TRANSFER FACILITY | PDF | R | 0.0015 | 2020-07-07 | Rev.0 | IFR | 0.0006 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-DRG-001 | HAZARDOUS AREA CLASSIFICATION LAYOUT | PDF | R | 0.0014 | 2020-08-05 | Rev.01 | IFA | 0.00091 | SUBMITTED REV.01
PROCESS | VTV-3281-LIT-9511-PR-DRG-002 | P&ID SYMBOLS AND IDENTIFICATION (S1) | PDF | A | 0.0014 | 2020-07-20 | Rev.02 | AFC | 0.00133 | SUBMITTED Rev.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-003 | BLOCK DIAGRAM (B1) | PDF | A | 0.0015 | 2020-07-06 | Rev.0 | AFC | 0.001425 | SUBMITTED
PROCESS | VTV-3281-LIT-9511-PR-DRG-004 | PROCESS FLOW DIAGRAM ‐ LPG IMPORT TERMINAL F1 | PDF | A | 0.0014 | 06-07-2020 | Rev.03 | AFC | 0.00133 | Comments recd on REV.03
PROCESS | VTV-3281-LIT-9511-PR-DRG-005 | PROCESS FLOW DIAGRAM ‐ LPG IMPORT TERMINAL F2 | PDF | A | 0.0014 | 26-07-2020 | Rev.03 | AFC | 0.00133 | Comments recd on REV.03
PROCESS | VTV-3281-LIT-9511-PR-DRG-006 | P&I DIAGRAM - INTER CONNECTION OF C/C LINES (P1D) | PDF | A | 0.0015 | 2020-07-10 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-007 | P&I DIAGRAM - NEW PROPANE STORAGE TANK T‐4301 (P2A) | PDF | A | 0.0015 | 2020-07-10 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-008 | P&I DIAGRAM - NEW PROPANE STORAGE TANK T‐4301 (P2B) | PDF | A | 0.0015 | 2020-07-10 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-009 | P&I DIAGRAM - SEPARATION AND DISTRIBUTION OF C/C PIPE LINES (P3) | PDF | A | 0.0015 | 2020-07-10 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-010 | P&I DIAGRAM - NEW BUTANE STORAGE TANK T‐5301 (P4A) | PDF | A | 0.0015 | 2020-07-10 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-011 | P&I DIAGRAM - NEW BUTANE STORAGE TANK T‐5301 (P4B) | PDF | A | 0.0015 | 2020-07-10 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-012 | P&I DIAGRAM - NEW FLASH GAS COMPRESSOR SUCTION SEPERATOR (B-2304A/B) (P5) | PDF | A | 0.0015 | 2020-07-10 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-013 | P&I DIAGRAM - FLASH GAS COMPRESSOR K‐2303.1A/2A (P6) | PDF | A | 0.0015 | 2020-07-10 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-014 | P&I DIAGRAM - FLASH GAS COMPRESSOR K‐2303.1B/2B (P7) | PDF | A | 0.0015 | 2020-07-10 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-015 | P&I DIAGRAM - BUFFER BULLETS‐PROPANE/BUTANE T-2303A/B (P8) | PDF | A | 0.0015 | 2020-07-10 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-016 | P&I DIAGRAM - NEW COOLING TOWER SYSTEM (U1) | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-017 | P&I DIAGRAM - EFFLUENT TREATMENT PLANT ETP (U2) | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-018 | P&I DIAGRAM - LPG/PROPANE EVAPORATOR AND CONDENSATE SEPARATOR | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-019 | P&I DIAGRAM - PROPANE STORAGE TANK T‐2301 | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-020 | P&I DIAGRAM - PROPANE STORAGE TANK T‐2301 | PDF | A | 0.0015 | 2020-07-17 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-021 | P&I DIAGRAM - SEPARATION AND DISTRIBUTION SECTION (EXISTING) | PDF | A | 0.0015 | 2020-07-17 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-022 | P&I DIAGRAM - BUTANE STORAGE TANK T‐3301 | PDF | A | 0.0015 | 2020-07-17 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-023 | P&I DIAGRAM - BUTANE STORAGE TANK T‐3301 | PDF | A | 0.0015 | 2020-07-17 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-024 | P&I DIAGRAM - BLENDING CONTROL SYSTEM | PDF | A | 0.0015 | 2020-07-17 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-025 | P&I DIAGRAM - EXISTING FLASH GAS COMPRESSOR‐K‐2301 - 1A / 2A | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-026 | P&I DIAGRAM - EXISTING FLASH GAS COMPRESSOR‐K‐2301 - 1B / 2B | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-027 | P&I DIAGRAM - FLASH GAS CONDENSATE SECTION | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-028 | P&I DIAGRAM - PROPANE HEATERS | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-029 | P&I DIAGRAM - BUTANE HEATERS | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-030 | P&I DIAGRAM - UTILITY (LP STEAM CONDENSATE SECTION) | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-031 | P&I DIAGRAM - COOLING WATER DISTRIBUTION | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-032 | P&I DIAGRAM - BUFFER BULLETS‐PROPANE/BUTANE T-2302A/B | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-033 | P&I DIAGRAM - FLARE SYSTEM | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-034 | P&I DIAGRAM - EXISTING DIESEL TRANSFER SYSTEM | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-035 | P&I DIAGRAM - LOADING OF ROAD TANKERS | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-036 | P&I DIAGRAM - LOADING OF RAIL TANKERS | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-037 | P&I DIAGRAM - LOADING OF RAIL TANKERS, UNLOADING OF SICK RAIL TANKERS SHEET 01 | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-038 | P&I DIAGRAM - LOADING OF RAIL TANKERS, UNLOADING OF SICK RAIL TANKERS SHEET 02 | PDF | A | 0.0015 | 2020-07-14 | Rev.02 | AFC | 0.001425 | SUBMITTED REV.02
PROCESS | VTV-3281-LIT-9511-PR-DRG-039 | UTILITY FLOW DIAGRAM‐COOLING WATER DISTRIBUTION TERMINAL‐F3 | PDF | A | 0.0014 | 2020-07-14 | Rev.0 | IFA | 0.00091 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-DRG-040 | UTILITY FLOW DIAGRAM‐STEAM, DIESEL INST AIR‐F4 | PDF | A | 0.0014 | 2020-07-14 | Rev.0 | IFA | 0.00091 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-DRG-041 | UTILITY FLOW DIAGRAM –ETP‐F5 | PDF | A | 0.0014 | 2020-07-14 | Rev.0 | IFA | 0.00091 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-DRG-042 | UTILITY FLOW DIAGRAM –PROCESS WATER, INST AIR, NITROGEN‐F6 | PDF | A | 0.0014 | 2020-07-14 | Rev.0 | IFA | 0.00091 | RECD COMMENTS ON REV.0
PROCESS | VTV-3281-LIT-9511-PR-DRG-045 | P&I DIAGRAM FOR YARD PIPING | PDF | A | 0.0014 | 2020-08-14 |  | IFA | 0.00091
PROCESS | VTV-3281-LIT-9511-PR-DRG-047 | UTILITY HOOK UP DIAGRAM (Y1) |  |  | 0.0014 | 2020-07-15 | Rev.0 | IFA | 0.00091 | SUBMITTED REV.0
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-001 | DESIGN CALCULATION REPORT FOR BARRICADING STRUCTURE | PDF | A | 0.0014 | 2020-05-19 |  | IFA | 0.00091
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-002 | SOIL INVESTIGATION REPORT | PDF | A | 0.0014 | 2020-06-30 |  | IFA | 0.00091
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-003 | DESIGN CALCULATION REPORT FOR PUMP PLATFORM (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-11-10 |  | IFA | 0.00091
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-004 | DESIGN CALCULATION REPORT FOR PSV PLATFORM (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-11-19 |  | IFA | 0.00091
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-005 | DESIGN CALCULATION REPORT FOR CIRCUMFERENTIAL WALKWAY (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-12-05 |  | IFA | 0.00091
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-006 | DESIGN CALCULATION REPORT FOR DOME CENTER WALKWAY (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-11-25 | REV.0 | IFA | 0.00091 | SUBMITTED REV.0
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-007 | DESIGN CALCULATION REPORT FOR PIPE RACK STEEL STRUCTURE (NEW TANK AREA) | PDF | A | 0.0014 | 2020-10-22 | REV.0 | IFA | 0.00091 | SUBMITTED REV.0
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-008 | DESIGN CALCULATION REPORT FOR PIPE RACK STEEL STRUCTURE (NEW COMPRESSOR AREA) | PDF | A | 0.0014 | 2020-11-05 |  | IFA | 0.00091
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-009 | DESIGN CALCULATION REPORT FOR PIPE RACK STEEL STRUCTURE (NEW LP BOILER AREA) | PDF | A | 0.0014 | 2020-11-07 |  | IFA | 0.00091
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-010 | DESIGN CALCULATION REPORT FOR STAIR TOWER (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-11-11 | REV.0 | IFA | 0.00091 | SUBMITTED REV.0
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-011 | DESIGN CALCULATION REPORT FOR PIPE BRIDGE WITH STAIR (T-4301 & T-5301) | PDF | A | 0.0014 | 2020-11-11 |  | IFA | 0.00091
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-012 | DESIGN CALCULATION REPORT FOR NEW COMPRESSOR SHED STEEL STRUCTURE | PDF | A | 0.0014 | 2020-12-18 |  | IFA | 0.00091
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-013 | DESIGN CALCULATION REPORT FOR SWITCHYARD STRUCTURES | PDF | A | 0.0014 | 2020-12-05 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-CAL-014 | DESIGN CALCULATION REPORT FOR CABLE TRAY RACK | PDF | A | 0.0014 | 2020-12-18 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-001 | LAYOUT & DETAILS OF PILE & PILE CAP OF BARRICADING FOUNDATION | PDF | A | 0.0014 | 2020-05-19 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-002 | LAYOUT & DETAILS OF PUMP PLATFORM (T-4301 & T-5301) | PDF | R | 0.0014 | 2020-11-10 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-003 | LAYOUT & DETAILS OF PSV PLATFORM (T-4301 & T-5301) | PDF | R | 0.0014 | 2020-11-19 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-004 | LAYOUT & DETAILS OF CIRCUMFERENCIAL WALKWAY (T-4301 & T-5301) | PDF | R | 0.0014 | 2020-12-05 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-005 | LAYOUT & DETAILS OF DOME CENTER WALKWAY (T-4301 & T-5301) | PDF | R | 0.0014 | 2020-11-25 | REV.0 | IFR | 0.00056 | SUBMITTED REV.0
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-006 | ROOF STRUCTURE LOADING DATA FOR T-4301 & T-5301 | PDF | R | 0.0014 | 2020-12-10 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-007 | LAYOUT & DETAILS OF NEW COMPRESSOR SHED STEEL STRUCTURE | PDF | R | 0.0014 | 2020-12-23 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-008 | LAYOUT & DETAILS OF STAIR TOWER (T-4301 & T-5301) | PDF | R | 0.0014 | 2020-11-18 | REV.0 | IFR | 0.00056 | SUBMITTED REV.0
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-009 | LAYOUT & DETAILS OF PIPE BRIDGE WITH STAIR (T-4301 & T-5301) | PDF | R | 0.0014 | 2020-11-21 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-011 | LAYOUT & DETAILS OF PIPE RACK STEEL STRUCTURE (NEW TANK AREA) | PDF | R | 0.0014 | 2020-10-26 | REV.0 | IFR | 0.00056 | SUBMITTED REV.0
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-012 | LAYOUT & DETAILS OF PIPE RACK STEEL STRUCTURE (NEW COMPRESSOR AREA) | PDF | R | 0.0014 | 2020-11-10 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-013 | LAYOUT & DETAILS OF PIPE RACK STEEL STRUCTURE (NEW LP BOILER AREA) | PDF | R | 0.0014 | 2020-11-13 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-014 | ARCH.DRAWING FOR COMPRESSOR SHED | PDF | R | 0.0014 | 2021-01-11 | REV.0 | IFR | 0.00056 | SUBMITTED REV.0
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-015 | STEEL STRUCTURE DETAIL DRAWINGS FOR CABLE TRAY RACK/ROAD CROSSINGS | PDF | R | 0.0014 | 2020-12-23 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-016 | PIPE SUPPORTS STRUCTURAL DRAWINGS | PDF | R | 0.0014 | 2021-01-25 |  | IFR | 0.00056
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-017 | STD. CAGE LADDER DRAWING | PDF | R | 0.0014 | 2020-09-17 | REV.01 | IFR | 0.00056 | SUBMITTED REV.01
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-018 | STD. GRATING DETAIL DRAWING | PDF | R | 0.0014 | 2020-09-17 | REV.01 | IFR | 0.00056 | SUBMITTED REV.01
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-019 | STD.STAIRCASE DRAWING | PDF | R | 0.0014 | 2020-09-17 | REV.02 | IFR | 0.00056 | COMMENTS RECD. ON REV.02
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-020 | STD.HANDRAIL DRAWING | PDF | R | 0.0014 | 2020-09-17 | REV.02 | IFR | 0.00056 | SUBMITTED REV.02
STRUCTURAL | VTV-3281-LIT-9511-ST-DRG-021 | STANDARD CONNECTION DETAILS FOR STEEL STRUCTURES | PDF | R | 0.0014 | 2020-09-17 |  | IFR | 0.00056
PROJECTS | VTV-3281-PROJ-001 | PROJECT SCHEDULE | PDF | R | 0.0014 | 2020-07-22 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-002 | PROJECT COMMUNICATION PLAN | PDF | I | 0.0014 | 2020-07-10 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-003 | PROCEDURE FOR DOCUMENT MANAGEMENT & CONTROL | PDF | I | 0.0014 | 2020-07-15 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-004 | PROJECT EXECUTION PLAN | PDF | I | 0.0014 | 2020-07-10 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-005 | PROJECT MANAGEMENT PLAN | PDF | I | 0.0014 | 2020-07-15 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-006 | VENDOR LIST/SUB SUPPLIER LIST | PDF | I | 0.0014 | 2020-08-12 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-007 | ENGINEERING MANAGEMENT PLAN | PDF | I | 0.0014 | 2020-07-25 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-008 | PROCEDURE MANAGEMENT PLAN | PDF | I | 0.0014 | 2020-07-30 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-009 | CONSTRUCTION MANAGEMENT PLAN | PDF | I | 0.0014 | 2020-07-30 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-010 | PROCEDURE FOR INTERNAL AUDIT | PDF | I | 0.0014 | 2020-07-15 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-011 | FORMAT PROGRESS REPORT (WEEKLY / MONTHLY) | PDF | I | 0.0014 | 2020-07-10 |  | AFC | 0.00133
PROJECTS | VTV-3281-PROJ-043 | PROJECT ORGANISATION CHART WITH KEY PERSONNEL QUALIFICATION DETAIL | PDF | I | 0.0014 | 2020-07-15 |  | AFC | 0.00133
PROCESS | 001 | bhanu | abc |  | 1 | 2026-08-27 | rev 2 | DUE | 0 | good

## Config
Key | Value
ElapsedDays | nan
ProjectCode | 11102
ProgressAsOn | nan
ProjectName | EPC for Ushodayam BioEnergy
ZeroDate | 2026-02-12 00:00:00
EndDate | 2026-12-31 00:00:00
TotalDuration | nan

## Snapshots
SnapshotDate | Week | Year | Discipline | AFC | IFC | IFA | IFR | IDC | DUE | Total | PlannedWtg | EarnedWtg | CompletionPct